## 5 Year Master
Header on row 3 is used for pivot schedules in this file. Header on row 2 is from CBA finance schedule source file | [8 empty] | Formula | [8 empty] | Formula | Total Costs | [8 empty] | Formula | Formula |  | Formula | Formula | Formula | New Column
Main Category | Subcategory | Project/Program | Program Subcategory | R&M Subcategory | Investment Classification | Commencement Year | Multi Year - Start Year | Single Year - Start Year | Project Type | Supplemental Y/N | TM1 Proposal Number | CBA Project Description | Composite Class | Depreciation Class | Customer | System | Function | Range | 2023 & Prior Years | 2024 | 2025 | 2026 | 2027 | 2028 | Total | Total With Prior Year | Future Years | Under/Over 750k
Main Cat | Sub Cat | Project/Program | Program Subcategory | R&M Subcategory | Investment Classification | Commencement Year | MY-Start Year | SY-Start Year | Project Type | Supplemental Y/N | TM1 | CBA Description | Composite Class | Depreciation Class | Customer | System | Function | Range | Prior Years | CY | CY+1 | CY+2 | CY+3 | CY+4 | Total new | Total With Prior Year | Future Year | Over 750 | Year Rank | Order Expenditure | Year 1 Expenditure | Order | 5 Year Plan | Rebudgeted in 2024 CBA | Last Column
Generation | Hydraulic Plant |  |  |  | Renewal | 2021 | 2021 |  | Multi Year | N | P144 | Refurbish Ebbegunbaeg Control Structure | [5 empty] | Over $5 Million | 9945.2 | 2781.6 | 4952.2 |  |  |  | 7733.8 | 17679 | 4952.2 | Yes | 10 |  | 9945.2 | 10.3018 | Yes
Transmission and Rural Operations | Terminal Stations |  |  |  | System Growth | 2021 | 2021 |  | Multi Year | N | P202 | Wabush Terminal Station Upgrades | [5 empty] | Over $5 Million | 8870.1 | 3808 |  |  |  |  | 3808 | 12678.1 | 0 | Yes | 10 |  | 8870.1 | 10.2013 | Yes | Y
Transmission and Rural Operations | Terminal Stations |  |  |  | System Growth | 2021 | 2021 |  | Multi Year | N | P184 | Additions for Load - Wabush Substation Upgrades | [5 empty] | Over $5 Million | 7439.7 | 2739.9 | 514.5 |  |  |  | 3254.4 | 10694.1 | 514.5 | Yes | 10 |  | 7439.7 | 10.3011 | Yes | Y
Transmission and Rural Operations | Generation |  |  |  | Renewal | 2022 | 2022 |  | Single Year | N | P461 | Diesel Genset Replacement Unit 2039 - St. Lewis | [5 empty] | $1 Million to $5 Million | 1980.8 | [5 empty] | 0 | 1980.8 | 0 | Yes | 9 |  | 1980.8 | 9.1002 | No
Transmission and Rural Operations | Generation |  |  |  | Renewal | 2022 | 2022 |  | Multi Year | N | P474 | Diesel Genset Replacement Unit 2012 - L'Anse-Au-Loup | [5 empty] | $1 Million to $5 Million | 2853.1 | 210.2 |  |  |  |  | 210.2 | 3063.3 | 0 | Yes | 9 |  | 2853.1 | 9.2003 | Yes
Transmission and Rural Operations | Metering |  |  |  | Service Enhancement | 2022 | 2022 |  | Multi Year | N | P514 | Replace Metering System | [5 empty] | Over $5 Million | 4881.2 | 994.6 |  |  |  |  | 994.6 | 5875.8 | 0 | Yes | 9 |  | 4881.2 | 9.2006 | Yes
Transmission and Rural Operations | Tools and Equipment |  |  |  | General Plant | 2022 | 2022 |  | Multi Year | N | P484 | Purchase 85' Material Handler Aerial Device on Track Unit | [5 empty] | $1 Million to $5 Million | 1286.1 | 67.8 |  |  |  |  | 67.8 | 1353.9 | 0 | Yes | 9 |  | 1286.1 | 9.2001 | Yes
Transmission and Rural Operations | Tools and Equipment |  |  |  | General Plant | 2022 | 2022 |  | Multi Year | N | P485 | Purchase 46' Material Handler Aerial Device on Track Unit | [5 empty] | $750,000 to $1 Million | 719.2 | 38.8 |  |  |  |  | 38.8 | 758 | 0 | Yes | 9 |  | 719.2 | 9.2001 | Yes
General Properties | Transportation |  |  |  | General Plant | 2022 | 2022 |  | Multi Year | N | P318 | Replace Light- and Heavy-Duty Vehicles (2022-2024) | [5 empty] | $1 Million to $5 Million | 1162.2 | 2319.6 |  |  |  |  | 2319.6 | 3481.8 | 0 | Yes | 9 |  | 1162.2 | 9.2003 | Yes
Generation | Hydraulic Plant | Major Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | Y | P717/P874 | Penstock Life Extension - Phase 1 (2023-2025) | [5 empty] | Over $5 Million | 2105 | 13172.6 | 35329.1 |  |  |  | 48501.7 | 50606.7 | 35329.1 | Yes | 8 |  | 2105 | 8.3051 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P612 | Replace Diesel Genset 1 (2023-2024) - Ebbegunbaeg | [5 empty] | $1 Million to $5 Million | 298 | 728.3 |  |  |  |  | 728.3 | 1026.3 | 0 | Yes | 8 |  | 298 | 8.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | N | P596 | Water System Condition Assessment and Upgrades (2023) - Bay d'Espoir | [5 empty] | Under $750,000 | 161 | 504.9 |  |  |  |  | 504.9 | 665.9 | 0 | No | 8 |  | 161 | 8.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P590 | Refurbish Superstructure (2023-2024) - Salmon River Spillway | [5 empty] | $1 Million to $5 Million | 328.3 | 2500 |  |  |  |  | 2500 | 2828.3 | 0 | Yes | 8 |  | 328.3 | 8.2003 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P631 | Replace Powerhouse Station Service Panel (2023-2024) - Upper Salmon | [5 empty] | $1 Million to $5 Million | 591.8 | 976.7 |  |  |  |  | 976.7 | 1568.5 | 0 | Yes | 8 |  | 591.8 | 8.2002 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | Y | P812 | Purchase and Replace Last Stage Blades - Holyrood Units 1 and 2 | [5 empty] | Over $5 Million | 3596.5 | 2812.2 |  |  |  |  | 2812.2 | 6408.7 | 0 | Yes | 8 |  | 3596.5 | 8.2006 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P662 | Replace Oil Mist Separator (2023-2024) - Happy Valley Gas Turbine | [5 empty] | Under $750,000 | 138.5 | 262.1 |  |  |  |  | 262.1 | 400.6 | 0 | No | 8 |  | 138.5 | 8.2 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Roll Up |  | Renewal | 2023 | 2023 |  | Multi Year | N | P602, P604, P620, P640, P652 | Terminal Station Renewal Program (2023-2024) | [5 empty] | Over $5 Million | 1733.7 | 5584.5 |  |  |  |  | 5584.5 | 7318.2 | 0 | Yes | 8 |  | 1733.7 | 8.2007 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2023 | 2023 |  | Multi Year | N | P597 | Major Condition Assessment and Miscellaneous Refurbishments Synchronous Condenser 1 and 2 (2023-2024) - Wabush Terminal Station | [5 empty] | $1 Million to $5 Million | 577.2 | 516.1 |  |  |  |  | 516.1 | 1093.3 | 0 | Yes | 8 |  | 577.2 | 8.2001 | Yes | Y
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2023 | 2023 |  | Multi Year | N | P619 | Circuit Breakers Renewal Program (2023-2024) | [5 empty] | $1 Million to $5 Million | 216.9 | 3595.1 |  |  |  |  | 3595.1 | 3812 | 0 | Yes | 8 |  | 216.9 | 8.2004 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Terminal Station Renewal Program |  | Renewal | 2023 | 2023 |  | Multi Year | N | P604 | Replace Instrument Transformers (2023-2024) - Various | [5 empty] | Under $750,000 | 127 | 381.2 |  |  |  |  | 381.2 | 508.2 | 0 | No | 8 |  | 127 | 8.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Terminal Station Renewal Program |  | Renewal | 2023 | 2023 |  | Multi Year | N | P620 | Replace Protective Relays (2023-2024) - Various | [5 empty] | $1 Million to $5 Million | 625.2 | 1334.5 |  |  |  |  | 1334.5 | 1959.7 | 0 | Yes | 8 |  | 625.2 | 8.2002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Terminal Station Renewal Program |  | Renewal | 2023 | 2023 |  | Multi Year | N | P602 | Replace Disconnects (2023-2024) - Various | [5 empty] | Under $750,000 | 128.7 | 524.1 |  |  |  |  | 524.1 | 652.8 | 0 | No | 8 |  | 128.7 | 8.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Terminal Station Renewal Program |  | Renewal | 2023 | 2023 |  | Multi Year | N | P652 | Upgrade Power Transformers (2023-2024) - Various | [5 empty] | $1 Million to $5 Million | 718.1 | 3261.2 |  |  |  |  | 3261.2 | 3979.3 | 0 | Yes | 8 |  | 718.1 | 8.2004 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Terminal Station Renewal Program |  | Renewal | 2023 | 2023 |  | Multi Year | N | P640 | Replace Terminal Station Battery Banks and Chargers (2023-2024) - Various | [5 empty] | Under $750,000 | 134.7 | 83.5 |  |  |  |  | 83.5 | 218.2 | 0 | No | 8 |  | 134.7 | 8.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P647 | Replace Data Alarm System Annunciators (2023) - Buchans | [5 empty] | Under $750,000 | 61.2 | 104.8 |  |  |  |  | 104.8 | 166 | 0 | No | 8 |  | 61.2 | 8.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P632 | Install Breaker Failure Protection (2023-2024) - Sunnyside | [5 empty] | Under $750,000 | 73.5 | 216.2 |  |  |  |  | 216.2 | 289.7 | 0 | No | 8 |  | 73.5 | 8.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P591 | Replace Circuit Breaker Reclosing Controllers (2023-2024) - Hardwoods | [5 empty] | Under $750,000 | 81.6 | 149.6 |  |  |  |  | 149.6 | 231.2 | 0 | No | 8 |  | 81.6 | 8.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | N | P588 | Install Fire Protection in 230 kV Stations (2023-2024) - Deer Lake | [5 empty] | Under $750,000 | 79.2 | 535.3 |  |  |  |  | 535.3 | 614.5 | 0 | No | 8 |  | 79.2 | 8.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Mandatory | 2023 | 2023 |  | Multi Year | N | P603 | Replace Terminal Station Lighting (2023-2024) | [5 empty] | $750,000 to $1 Million | 323.3 | 594.1 |  |  |  |  | 594.1 | 917.4 | 0 | Yes | 8 |  | 323.3 | 8.2001 | Yes | Y
Transmission and Rural Operations | Terminal Stations | Project |  |  | System Growth | 2023 | 2023 |  | Multi Year | N | P649 | Additions for Load Growth - Upgrade Transformer Capacity (2023-2024) - Jean Lake Terminal Station | [5 empty] | Over $5 Million | 580 | 0 | 5436.1 |  |  |  | 5436.1 | 6016.1 | 5436.1 | Yes | 8 |  | 580 | 8.3006 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2023 | 2023 |  | Multi Year | N | P594 | Install Oil Spill Containment Transformer T1S (2023-2024) - Cat Arm | [5 empty] | Under $750,000 | 155.1 | 426.5 |  |  |  |  | 426.5 | 581.6 | 0 | No | 8 |  | 155.1 | 8.2001 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2023 | 2023 |  | Multi Year | N | P669 | Upgrade of Worst-Performing Distribution Feeders (2023-2024) | [5 empty] | $1 Million to $5 Million | 73.4 | 1372.6 |  |  |  |  | 1372.6 | 1446 | 0 | Yes | 8 |  | 73.4 | 8.2001 | Yes
Transmission and Rural Operations | Generation | Major Project |  |  | Service Enhancement | 2023 | 2023 |  | Multi Year | Y | P851 | Long-Term Supply for Southern Labrador - Phase 1 | [5 empty] | Over $5 Million | 1835 | 17812 | 40116.3 | 23327.6 | 3304.3 |  | 84560.2 | 86395.2 | 66748.2 | Yes | 8 |  | 1835 | 8.5086 | Yes | Y
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | 2023 | 2023 |  | Multi Year | N | P610 | Diesel Genset Replacement Unit 2053 - Hopedale (note I reforecast this one to match the changes to the full program from Greg so the check sum on the pivot tables worked) | [5 empty] | $1 Million to $5 Million | 819.1 | 174 | 1883.1 | 250 |  |  | 2307.1 | 3126.2 | 2133.1 | Yes | 8 |  | 819.1 | 8.4003 | Yes
Transmission and Rural Operations | Generation | Program | Roll Up |  | Renewal | 2023 | 2023 |  | Multi Year | N | P610, P614 | Diesel Genset Replacement Program (2023-2025) | [5 empty] | $1 Million to $5 Million | 819.1 | 174 | 1883.1 | 250 |  |  | 2307.1 | 3126.2 | 2133.1 | Yes | 8 |  | 819.1 | 8.4003 | Yes
Transmission and Rural Operations | Generation | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | N | P637 | Replace Building Exterior (2023-2024) - Postville | [5 empty] | Under $750,000 | 124.6 | 558.7 |  |  |  |  | 558.7 | 683.3 | 0 | No | 8 |  | 124.6 | 8.2001 | Yes
Transmission and Rural Operations | Generation | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P615 | Replace Intermediate Fuel Storage Tanks (2023-2024) - Nain | [5 empty] | Under $750,000 | 127.4 | 593.7 |  |  |  |  | 593.7 | 721.1 | 0 | No | 8 |  | 127.4 | 8.2001 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | N | P626 | Replace HVAC System (2023-2024) - Bishop's Falls | [5 empty] | Under $750,000 | 43.4 | 128.8 |  |  |  |  | 128.8 | 172.2 | 0 | No | 8 |  | 43.4 | 8.2 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | N | P663 | Upgrade Water and Fire Suppression Systems (2023-2024) - Bishop's Falls | [5 empty] | $1 Million to $5 Million | 353.7 | 2886.3 |  |  |  |  | 2886.3 | 3240 | 0 | Yes | 8 |  | 353.7 | 8.2003 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | N | P668 | Replace Diesel Shop Building (2023-2025) - Bishop's Falls | [5 empty] | $1 Million to $5 Million | 168 | 1254.1 | 889.9 |  |  |  | 2144 | 2312 | 889.9 | Yes | 8 |  | 168 | 8.3002 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2023 | 2023 |  | Multi Year | N | P656 | Replace Mobile Equipment (2023-2024) | [5 empty] | Under $750,000 | 541.2 | 187.3 |  |  |  |  | 187.3 | 728.5 | 0 | No | 8 |  | 541.2 | 8.2001 | Yes
General Properties | Telecontrol | Project |  |  | Renewal | 2023 | 2023 |  | Multi Year | N | P638 | Replace Power Line Carrier (2023–2024) - TL223 and TL224 | [5 empty] | $750,000 to $1 Million | 105.3 | 852.4 |  |  |  |  | 852.4 | 957.7 | 0 | Yes | 8 |  | 105.3 | 8.2001 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2023 | 2023 |  | Multi Year | N | P665 | Replace Light- and Heavy-Duty Vehicles (2023-2025) | [5 empty] | $1 Million to $5 Million | 1308.1 | 2584.6 | 473.3 |  |  |  | 3057.9 | 4366 | 473.3 | Yes | 8 |  | 1308.1 | 8.3004 | Yes
General Properties | Transportation | Project |  |  | General Plant | 2023 | 2023 |  | Multi Year | Y |  | Ultra-Fast Direct-Current EV Chargers - Purchase and Installation | [5 empty] | $1 Million to $5 Million | 62.5 | 1766 | 231.3 |  |  |  | 1997.3 | 2059.8 | 231.3 | Yes | 8 |  | 62.5 | 8.3002 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2024 |  | 2024 | Single Year | N | P766 | Overhaul Unit 1 (2024) - Granite Canal | [5 empty] | Under $750,000 |  | 323.8 |  |  |  |  | 323.8 | 323.8 | 0 | No | 7 |  | 323.8 | 7.1 | Yes
Generation | Hydraulic Plant | Program | Roll Up |  | Renewal | 2024 |  | 2024 | Single Year | N |  | Overhaul Hydraulic Units (2024) | [5 empty] | Under $750,000 |  | 323.8 |  |  |  |  | 323.8 | 323.8 | 0 | No | 7 |  | 323.8 | 7.1 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P761 | Hydraulic In-Service Failures (2024) | [5 empty] | $1 Million to $5 Million |  | 1500 |  |  |  |  | 1500 | 1500 | 0 | Yes | 7 |  | 1500 | 7.1002 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P773 | Penstock Level II Condition Assessment (2024) - Upper Salmon | [5 empty] | Under $750,000 |  | 382.8 |  |  |  |  | 382.8 | 382.8 | 0 | No | 7 |  | 382.8 | 7.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P824 | Replace Annunciator Panels (2024-2025) - Cat Arm | [5 empty] | Under $750,000 |  | 160.2 | 191.2 |  |  |  | 351.4 | 351.4 | 191.2 | No | 7 |  | 160.2 | 7.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P825 | Replace Annunciator - Phase 2 (2024-2025) - Bay d'Espoir | [5 empty] | Under $750,000 |  | 294.1 | 187.5 |  |  |  | 481.6 | 481.6 | 187.5 | No | 7 |  | 294.1 | 7.2 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P799 | Replace Powerhouse 1 Roof (2024-2025) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  | 140.2 | 1819.2 |  |  |  | 1959.4 | 1959.4 | 1819.2 | Yes | 7 |  | 140.2 | 7.2002 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P759 | Replace Powerhouse 1 Air Conditioning Unit (2024-2025) - Bay d'Espoir | [5 empty] | Under $750,000 |  | 57.8 | 231.2 |  |  |  | 289 | 289 | 231.2 | No | 7 |  | 57.8 | 7.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P795 | Flatten Downstream Slope (2024-2025) - Hinds Lake | [5 empty] | $1 Million to $5 Million |  | 276.1 | 2953.4 |  |  |  | 3229.5 | 3229.5 | 2953.4 | Yes | 7 |  | 276.1 | 7.2003 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2024 |  | 2024 | Single Year | N | P860 | Replace Timber Crib and Insulation (2024) - Burnt Dam Spillway | [5 empty] | Under $750,000 |  | 161.8 |  |  |  |  | 161.8 | 161.8 | 0 | No | 7 |  | 161.8 | 7.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P782 | Refurbish Surge Tank 1 (2024-2025) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  | 175.8 | 2111.4 |  |  |  | 2287.2 | 2287.2 | 2111.4 | Yes | 7 |  | 175.8 | 7.2002 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P767 | Refurbish Intake 1 (2024-2025) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  | 272.1 | 3071.9 |  |  |  | 3344 | 3344 | 3071.9 | Yes | 7 |  | 272.1 | 7.2003 | Yes |  |  |  | MOVED from 2021 to 2022
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | 2024 |  | 2024 | Single Year | N | P853 | Install Anemometer (2024) - Cat Arm | [5 empty] | Under $750,000 |  | 68.6 |  |  |  |  | 68.6 | 68.6 | 0 | No | 7 |  | 68.6 | 7.1 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P780 | Thermal In-Service Failures (2024) | [5 empty] | $1 Million to $5 Million |  | 3508.7 |  |  |  |  | 3508.7 | 3508.7 | 0 | Yes | 7 |  | 3508.7 | 7.1004 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P762 | Boiler Condition Assessment and Miscellaneous Upgrades (2024) - Holyrood | [5 empty] | $1 Million to $5 Million |  | 3957.8 |  |  |  |  | 3957.8 | 3957.8 | 0 | Yes | 7 |  | 3957.8 | 7.1004 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P802 | Overhaul Unit 1 Turbine Valves and Generator (2024) - Holyrood | [5 empty] | Over $5 Million |  | 5181.4 |  |  |  |  | 5181.4 | 5181.4 | 0 | Yes | 7 |  | 5181.4 | 7.1005 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P779 | Overhaul Pumps (2024) - Holyrood | [5 empty] | Under $750,000 |  | 661 |  |  |  |  | 661 | 661 | 0 | No | 7 |  | 661 | 7.1001 | Yes
Generation | Thermal Plant | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P857 | Refurbish Outbuilding and Powerhouse Building Envelopes (2024-2025) - Holyrood | [5 empty] | $1 Million to $5 Million |  | 156.2 | 1039.4 |  |  |  | 1195.6 | 1195.6 | 1039.4 | Yes | 7 |  | 156.2 | 7.2001 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2024 |  | 2024 | Single Year | N | P790 | Overhaul Marine Terminal Loading Arms (2024) - Holyrood | [5 empty] | Under $750,000 |  | 511 |  |  |  |  | 511 | 511 | 0 | No | 7 |  | 511 | 7.1001 | Yes
Generation | Thermal Plant | Project |  |  | Mandatory | 2024 |  | 2024 | Single Year | N | P797 | Refurbish Fuel Oil Storage Tank 4 (2024) - Holyrood | [5 empty] | $1 Million to $5 Million |  | 1920 |  |  |  |  | 1920 | 1920 | 0 | Yes | 7 |  | 1920 | 7.1002 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P809 | Upgrade UPS 1 & 2 (2024-2025) - Holyrood | [5 empty] | Under $750,000 |  | 263 | 107.6 |  |  |  | 370.6 | 370.6 | 107.6 | No | 7 |  | 263 | 7.2 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P820 | Upgrade Unit 1 Control System (2024-2025) - Holyrood | [5 empty] | Under $750,000 |  | 468.3 | 184.3 |  |  |  | 652.6 | 652.6 | 184.3 | No | 7 |  | 468.3 | 7.2001 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P803 | Upgrade DCS Hardware - Units 1 and 2 (2024-2025) - Holyrood | [5 empty] | Under $750,000 |  | 195.2 | 277.3 |  |  |  | 472.5 | 472.5 | 277.3 | No | 7 |  | 195.2 | 7.2 | Yes
Generation | Gas Turbines | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P758 | Gas Turbine In-Service Failures (2024) | [5 empty] | Under $750,000 |  | 358 |  |  |  |  | 358 | 358 | 0 | No | 7 |  | 358 | 7.1 | Yes
Generation | Gas Turbines | Project |  |  | Service Enhancement | 2024 | 2024 |  | Multi Year | N | P791 | Construct Maintenance Platform (2024-2025) - Holyrood Gas Turbine | [5 empty] | Under $750,000 |  | 130.5 | 228.7 |  |  |  | 359.2 | 359.2 | 228.7 | No | 7 |  | 130.5 | 7.2 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2024 |  | 2024 | Single Year | N | P832 | Inspect Fuel Tanks (2024) - Hardwoods Gas Turbines | [5 empty] | Under $750,000 |  | 692.9 |  |  |  |  | 692.9 | 692.9 | 0 | No | 7 |  | 692.9 | 7.1001 | Yes
Generation | Gas Turbines | Project |  |  | Service Enhancement | 2024 | 2024 |  | Multi Year | N | P828 | Upgrade Instrumentation (2024-2025) - Hardwoods Gas Turbine | [5 empty] | Under $750,000 |  | 60.9 | 157.2 |  |  |  | 218.1 | 218.1 | 157.2 | No | 7 |  | 60.9 | 7.2 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P763 | Purchase Tools and Equipment Less than $50,000 (2024) - Hydraulic Plants | [5 empty] | Under $750,000 |  | 209.4 |  |  |  |  | 209.4 | 209.4 | 0 | No | 7 |  | 209.4 | 7.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P764 | Purchase Tools and Equipment Less than $50,000 (2024) - Thermal Plants | [5 empty] | Under $750,000 |  | 167.1 |  |  |  |  | 167.1 | 167.1 | 0 | No | 7 |  | 167.1 | 7.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P765 | Purchase Tools and Equipment Less than $50,000 (2024) - Gas Turbine | [5 empty] | Under $750,000 |  | 18.6 |  |  |  |  | 18.6 | 18.6 | 0 | No | 7 |  | 18.6 | 7.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P805 | Renew Circuit Breakers (2024–2025) | [5 empty] | $1 Million to $5 Million |  | 183.9 | 2779.3 |  |  |  | 2963.2 | 2963.2 | 2779.3 | Yes | 7 |  | 183.9 | 7.2003 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P768 | Terminal Station In-Service Failures (2024) | [5 empty] | $1 Million to $5 Million |  | 1300 |  |  |  |  | 1300 | 1300 | 0 | Yes | 7 |  | 1300 | 7.1001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P769 | Replace Instrument Transformers (2024–2025) | [5 empty] | $750,000 to $1 Million |  | 154.9 | 714.8 |  |  |  | 869.7 | 869.7 | 714.8 | Yes | 7 |  | 154.9 | 7.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P810 | Replace Protective Relays (2024–2025) | [5 empty] | $1 Million to $5 Million |  | 1388.4 | 2050.7 |  |  |  | 3439.1 | 3439.1 | 2050.7 | Yes | 7 |  | 1388.4 | 7.2003 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P770 | Replace Disconnects (2024–2025) | [5 empty] | $1 Million to $5 Million |  | 127.4 | 1358.1 |  |  |  | 1485.5 | 1485.5 | 1358.1 | Yes | 7 |  | 127.4 | 7.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P846 | Upgrade Power Transformers (2024-2025) | [5 empty] | $1 Million to $5 Million |  | 864.6 | 2711.3 |  |  |  | 3575.9 | 3575.9 | 2711.3 | Yes | 7 |  | 864.6 | 7.2004 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P771 | Replace Terminal Station Battery Banks and Chargers (2024–2025) | [5 empty] | Under $750,000 |  | 71.8 | 120.9 |  |  |  | 192.7 | 192.7 | 120.9 | No | 7 |  | 71.8 | 7.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project | Standalone |  | General Plant | 2024 | 2024 |  | Multi Year | N | P743 | Install Fire Protection in 230 kV Stations (2024–2025) - Voisey's Bay | [5 empty] | Under $750,000 |  | 53.8 | 599 |  |  |  | 652.8 | 652.8 | 599 | No | 7 |  | 53.8 | 7.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P839 | Refurbish Control Building (2024-2025) - Grandy Brook and Doyles | [5 empty] | Under $750,000 |  | 109.4 | 444.7 |  |  |  | 554.1 | 554.1 | 444.7 | No | 7 |  | 109.4 | 7.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P822 | Upgrade Data Alarm Systems (2024–2025) - Western Avalon Terminal Station | [5 empty] | Under $750,000 |  | 137 | 156.9 |  |  |  | 293.9 | 293.9 | 156.9 | No | 7 |  | 137 | 7.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P821 | Replace Circuit Breaker Reclosing Controllers (2024–2025) - TL247 | [5 empty] | Under $750,000 |  | 112.4 | 215.8 |  |  |  | 328.2 | 328.2 | 215.8 | No | 7 |  | 112.4 | 7.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Mandatory | 2024 | 2024 |  | Multi Year | N | P772 | Upgrade Station Lighting (2024-2025) - Bottom Waters, Deer Lake, Doyles, Indian River, and Western Avalon Terminal Stations | [5 empty] | Under $750,000 |  | 91.6 | 429 |  |  |  | 520.6 | 520.6 | 429 | No | 7 |  | 91.6 | 7.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2024 | 2024 |  | Multi Year | N | P872 | [] | [5 empty] | Over $5 Million | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | Yes | 7 |  | 0 | 7.3008 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2024 | 2024 |  | Multi Year | Y | P872 | Purchase Spare Generator Step-Up Transformer | [5 empty] | Over $5 Million | 722.9 | 3420.4 | 3643 |  |  |  | 7063.4 | 7786.3 | 3643 | Yes | 7 |  | 722.9 | 7.3008 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P858 | Transmission In-Service Failures (2024) | [5 empty] | Under $750,000 |  | 158.5 |  |  |  |  | 158.5 | 158.5 | 0 | No | 7 |  | 158.5 | 7.1 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P859 | Wood Pole Line Management (2024) | [5 empty] | $1 Million to $5 Million |  | 3765.2 |  |  |  |  | 3765.2 | 3765.2 | 0 | Yes | 7 |  | 3765.2 | 7.1004 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Access | 2024 |  | 2024 | Single Year | N | P868 | Provide Service Extensions (2024) | [5 empty] | $1 Million to $5 Million |  | 4272 |  |  |  |  | 4272 | 4272 | 0 | Yes | 7 |  | 4272 | 7.1004 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P870 | Distribution System In-Service Failures, Miscellaneous Upgrades, and Street Lights (2024) | [5 empty] | $1 Million to $5 Million |  | 4345.4 |  |  |  |  | 4345.4 | 4345.4 | 0 | Yes | 7 |  | 4345.4 | 7.1004 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2024 | 2024 |  | Multi Year | N | P835 | Upgrade Worst-Performing Distribution Feeders (2024-2025) | [5 empty] | $1 Million to $5 Million |  | 1064.3 | 2227.4 |  |  |  | 3291.7 | 3291.7 | 2227.4 | Yes | 7 |  | 1064.3 | 7.2003 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2024 | 2024 |  | Multi Year | N | P776 | Renew Distribution Feeders (2024-2025) | [5 empty] | $1 Million to $5 Million |  | 1287.3 | 1245.1 |  |  |  | 2532.4 | 2532.4 | 1245.1 | Yes | 7 |  | 1287.3 | 7.2003 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P827 | Upgrade Distribution (2024-2025) - Bay d'Espoir Terminal Station 2 | [5 empty] | Under $750,000 |  | 93.2 | 331.5 |  |  |  | 424.7 | 424.7 | 331.5 | No | 7 |  | 93.2 | 7.2 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | System Growth | 2024 | 2024 |  | Multi Year | Y | P849 | Additions for Load Growth - Distribution System - Labrador City Duley Lake, Walsh River, and Landfill Sites (2024-2025) | [5 empty] | Under $750,000 |  | 37.9 | 191.3 |  |  |  | 229.2 | 229.2 | 191.3 | No | 7 |  | 37.9 | 7.2 | Yes
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | 2024 | 2024 |  | Multi Year | N | P777 | Diesel Genset Replacement Unit 2085 (2024-2025) - Nain | [5 empty] | $1 Million to $5 Million |  | 299.1 | 232.2 | 2363.3 |  |  | 2894.6 | 2894.6 | 2595.5 | Yes | 7 |  | 299.1 | 7.3003 | Yes
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | 2024 | 2024 |  | Multi Year | N | P778 | Diesel Genset Replacement Unit 3033 (2024-2025) - Makkovik | [5 empty] | $1 Million to $5 Million |  | 236.7 | 245.8 | 1539 |  |  | 2021.5 | 2021.5 | 1784.8 | Yes | 7 |  | 236.7 | 7.3002 | Yes
Transmission and Rural Operations | Generation | Program | Roll Up |  | Renewal | 2024 | 2024 |  | Multi Year | N |  | Replace Diesel Gensets (2024-2026) | [5 empty] | $1 Million to $5 Million |  | 535.8 | 478 | 3902.3 |  |  | 4916.1 | 4916.1 | 4380.3 | Yes | 7 |  | 535.8 | 7.3005 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P854 | Overhaul Diesel Units (2024) | [5 empty] | $750,000 to $1 Million |  | 829.2 |  |  |  |  | 829.2 | 829.2 | 0 | Yes | 7 |  | 829.2 | 7.1001 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P819 | Diesel In-Service Failures (2024) | [5 empty] | Under $750,000 |  | 488.3 |  |  |  |  | 488.3 | 488.3 | 0 | No | 7 |  | 488.3 | 7.1 | Yes
Transmission and Rural Operations | Generation | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P816 | Purchase Accommodations Trailer (2024-2025) - Makkovik and Cartwright | [5 empty] | $1 Million to $5 Million |  | 130.9 | 1420.2 |  |  |  | 1551.1 | 1551.1 | 1420.2 | Yes | 7 |  | 130.9 | 7.2002 | Yes
Transmission and Rural Operations | Metering | Program | Standalone |  | Access | 2024 |  | 2024 | Single Year | N | P862 | Purchase Meters and Metering Equipment (2024) | [5 empty] | Under $750,000 |  | 470.7 |  |  |  |  | 470.7 | 470.7 | 0 | No | 7 |  | 470.7 | 7.1 | Yes
Transmission and Rural Operations | Metering | Project |  |  | Service Enhancement | 2024 | 2024 |  | Multi Year | N | P833 | Automate Bulk Metering (2024-2026) | [5 empty] | $750,000 to $1 Million |  | 302.6 | 214.4 | 235.3 |  |  | 752.3 | 752.3 | 449.7 | Yes | 7 |  | 302.6 | 7.3001 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P871 | Purchase Tools and Equipment Less than $50,000 (2024) - Central Region | [5 empty] | Under $750,000 |  | 188.2 |  |  |  |  | 188.2 | 188.2 | 0 | No | 7 |  | 188.2 | 7.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P875 | Purchase Tools and Equipment Less than $50,000 (2024) - Northern Region | [5 empty] | Under $750,000 |  | 97 |  |  |  |  | 97 | 97 | 0 | No | 7 |  | 97 | 7.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P876 | Purchase Tools and Equipment Less than $50,000 (2024) - Labrador Region | [5 empty] | Under $750,000 |  | 120.1 |  |  |  |  | 120.1 | 120.1 | 0 | No | 7 |  | 120.1 | 7.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2024 |  | 2024 | Multi Year | N | P841 | Replace Mobile Equipment (2024-2025) | [5 empty] | $750,000 to $1 Million |  | 216.9 | 599.7 |  |  |  | 816.6 | 816.6 | 599.7 | Yes | 7 |  | 216.9 | 7.2001 | Yes
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | 2024 |  | 2024 | Single Year | N | P834 | Replace Grader Unit V9829 (2024) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  | 836.7 |  |  |  |  | 836.7 | 836.7 | 0 | Yes | 7 |  | 836.7 | 7.1001 | Yes
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | 2024 |  | 2024 | Multi Year | N | P838 | Purchase 50' Material Handler Aerial Device on Tracked Unit (2024-2026) - Happy Valley Goose Bay | [5 empty] | $750,000 to $1 Million |  | 24 | 841.8 | 7.1 |  |  | 872.9 | 872.9 | 848.9 | Yes | 7 |  | 24 | 7.3001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P785 | Upgrade Energy Management System (2024) | [5 empty] | Under $750,000 |  | 366.4 |  |  |  |  | 366.4 | 366.4 | 0 | No | 7 |  | 366.4 | 7.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P788 | Perform Software Upgrades and Minor Enhancements (2024) | [5 empty] | $750,000 to $1 Million |  | 864.2 |  |  |  |  | 864.2 | 864.2 | 0 | Yes | 7 |  | 864.2 | 7.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P784 | Update Cyber Security Infrastructure (2024) | [5 empty] | Under $750,000 |  | 281.3 |  |  |  |  | 281.3 | 281.3 | 0 | No | 7 |  | 281.3 | 7.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P745 | Purchase Personal Computers (2024) | [5 empty] | Under $750,000 |  | 555.9 |  |  |  |  | 555.9 | 555.9 | 0 | No | 7 |  | 555.9 | 7.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P747 | Replace Peripheral Infrastructure (2024) | [5 empty] | Under $750,000 |  | 276.8 |  |  |  |  | 276.8 | 276.8 | 0 | No | 7 |  | 276.8 | 7.1 | Yes |  |  | combined with bear brook into an assessment
General Properties | Information Systems | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P783 | Upgrade Core OT Infrastructure (2024) | [5 empty] | Under $750,000 |  | 174.7 |  |  |  |  | 174.7 | 174.7 | 0 | No | 7 |  | 174.7 | 7.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P865 | Telecommunications In-Service Failure (2024) | [5 empty] | Under $750,000 |  | 91.4 |  |  |  |  | 91.4 | 91.4 | 0 | No | 7 |  | 91.4 | 7.1 | Yes |  |  | (oper. Ring, linkages, wicket gates, head cover, servos) | renamed and scope added, removed as a capital job where it is FEED. Was Major overhaul of Unit 7 Turbine - BDE was 500 in 2023, 5000 in 2024, 2500 in 2025
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P786 | Purchase Mobile Devices (2024) | [5 empty] | Under $750,000 |  | 155.6 |  |  |  |  | 155.6 | 155.6 | 0 | No | 7 |  | 155.6 | 7.1 | Yes |  |  |  | MOVED from 2024 to 2023 in 2022 CBA prep
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P818 | Purchase Tools and Equipment Less than $50,000 (2024) - Telecontrol | [5 empty] | Under $750,000 |  | 45.6 |  |  |  |  | 45.6 | 45.6 | 0 | No | 7 |  | 45.6 | 7.1 | Yes |  |  | this may be an under $50k
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P800 | Replace 48 V Battery Banks and Chargers (2024) | [5 empty] | Under $750,000 |  | 422.2 |  |  |  |  | 422.2 | 422.2 | 0 | No | 7 |  | 422.2 | 7.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P847 | Replace Network Communications Equipment (2024) | [5 empty] | Under $750,000 |  | 180.7 |  |  |  |  | 180.7 | 180.7 | 0 | No | 7 |  | 180.7 | 7.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P861 | Minor Telecommunications Enhancements (2024) | [5 empty] | Under $750,000 |  | 96.9 |  |  |  |  | 96.9 | 96.9 | 0 | No | 7 |  | 96.9 | 7.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2024 |  | 2024 | Single Year | N | P774 | Upgrade Remote Terminal Units (2024) | [5 empty] | Under $750,000 |  | 165.9 |  |  |  |  | 165.9 | 165.9 | 0 | No | 7 |  | 165.9 | 7.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2024 |  | 2024 | Single Year | N | P842 | Replace CCTV Cameras (2024) | [5 empty] | Under $750,000 |  | 317.6 |  |  |  |  | 317.6 | 317.6 | 0 | No | 7 |  | 317.6 | 7.1 | Yes
General Properties | Telecontrol | Project |  |  | Renewal | 2024 | 2024 |  | Multi Year | N | P814 | Replace Power Line Carrier (2024-2025) - TL247 | [5 empty] | $750,000 to $1 Million |  | 87.2 | 667.4 |  |  |  | 754.6 | 754.6 | 667.4 | Yes | 7 |  | 87.2 | 7.2001 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P808 | Replace VHF Radio System (2024-2025) | [5 empty] | $1 Million to $5 Million |  | 1261.6 | 290.6 |  |  |  | 1552.2 | 1552.2 | 290.6 | Yes | 7 |  | 1261.6 | 7.2002 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2024 |  | 2024 | Single Year | N | P836 | Replace SONET Multiplexors (2024) | [5 empty] | Under $750,000 |  | 430.4 |  |  |  |  | 430.4 | 430.4 | 0 | No | 7 |  | 430.4 | 7.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2024 |  | 2024 | Single Year | N | P848 | Upgrade SCADA Network (2024) | [5 empty] | Under $750,000 |  | 402.3 |  |  |  |  | 402.3 | 402.3 | 0 | No | 7 |  | 402.3 | 7.1 | Yes |  |  |  | added nov 22
General Properties | Telecontrol | Project |  |  | General Plant | 2024 | 2024 |  | Multi Year | N | P804 | Replace MDR8000 Microwave Radios (2024-2025) | [5 empty] | $1 Million to $5 Million |  | 953.5 | 500.3 |  |  |  | 1453.8 | 1453.8 | 500.3 | Yes | 7 |  | 953.5 | 7.2001 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2024 | 2024 |  | Multi Year | N | P850 | Replace Light- and Heavy-Duty Vehicles (2024-2026) | [5 empty] | Over $5 Million |  | 1479.1 | 4148.8 | 8.4 |  |  | 5636.3 | 5636.3 | 4157.2 | Yes | 7 |  | 1479.1 | 7.3006 | Yes
General Properties | Administration | Program | Standalone |  | General Plant | 2024 |  | 2024 | Single Year | N | P863 | Purchase Office Equipment Less Than $50,000 (2024) | [5 empty] | Under $750,000 |  | 50 |  |  |  |  | 50 | 50 | 0 | No | 7 |  | 50 | 7.1 | Yes
General Properties | Administration | Program | Standalone |  | Service Enhancement | 2024 |  | 2024 | Single Year | N | P823 | Remove Safety Hazards (2024) | [5 empty] | Under $750,000 |  | 198.3 |  |  |  |  | 198.3 | 198.3 | 0 | No | 7 |  | 198.3 | 7.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2024 |  | 2024 | Single Year | N | P826 | General Property Rehabilitation (2024) - Hydro Place | [5 empty] | Under $750,000 |  | 234 |  |  |  |  | 234 | 234 | 0 | No | 7 |  | 234 | 7.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2024 |  | 2024 | Single Year | N | P801 | Upgrade HVAC Supervisory Controllers (2024) - Hydro Place | [5 empty] | Under $750,000 |  | 149.6 |  |  |  |  | 149.6 | 149.6 | 0 | No | 7 |  | 149.6 | 7.1 | Yes |  |  |  | was originally two separate projects, combined into one on LTAP request.
Allowance for Unforeseen Items |  | Program | Standalone |  | Allowance for Unforeseen | 2024 |  | 2024 | Single Year | N | N/A | Allowance for Unforeseen Items (2024) | [5 empty] | $1 Million to $5 Million |  | 1000 |  |  |  |  | 1000 | 1000 | 0 | Yes | 7 |  | 1000 | 7.1001 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Overhaul Unit 2 (2025) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  | 300 |  |  |  | 300 | 300 | 0 | No | 6 |  | 300 | 6.1 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Overhaul Unit 1 (2025) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  | 300 |  |  |  | 300 | 300 | 0 | No | 6 |  | 300 | 6.1 | Yes
Generation | Hydraulic Plant | Program | Roll Up |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Overhaul Hydraulic Units (2025) | [5 empty] | Under $750,000 |  |  | 600 |  |  |  | 600 | 600 | 0 | No | 6 |  | 600 | 6.1001 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Hydraulic In-Service Failures (2025) | [5 empty] | $1 Million to $5 Million |  |  | 1569 |  |  |  | 1569 | 1569 | 0 | Yes | 6 |  | 1569 | 6.1002 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Penstock Level II Condition Assessment (2025) - Granite Canal | [5 empty] | Under $750,000 |  |  | 200 |  |  |  | 200 | 200 | 0 | No | 6 |  | 200 | 6.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Unit 1 and Unit 2 Major Refurbishment (2025) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  |  | 1000 |  |  |  | 1000 | 1000 | 0 | Yes | 6 |  | 1000 | 6.1001 | Yes |  |  | was WAV
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Level II Condition Assessment Powerhouse Roof (2025) - Hinds Lake | [5 empty] | Under $750,000 |  |  | 100 |  |  |  | 100 | 100 | 0 | No | 6 |  | 100 | 6.1 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2025 | 2025 |  | Single Year | N |  | Rehabilitate Access Roads (2025-2026) - Hinds Lake | [5 empty] | $1 Million to $5 Million |  |  | 1150 |  |  |  | 1150 | 1150 | 0 | Yes | 6 |  | 1150 | 6.1001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Controllers (2025-2028) - Granite Canal | [5 empty] | $1 Million to $5 Million |  |  | 500 | 500 | 500 | 500 | 2000 | 2000 | 1500 | Yes | 6 |  | 500 | 6.4002 | Yes |  |  |  | MOVED from 2024 to 2023 to provide more notice to Vale on specifically assigned change for VBN project
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Powerhouse Septic System (2025-2026) - Upper Salmon | [5 empty] | Under $750,000 |  |  | 50 | 200 |  |  | 250 | 250 | 200 | No | 6 |  | 50 | 6.2 | Yes |  |  | changed to various as per Brad Eddy Feb 10 | advanced due to PCB concerns
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Refurbish Draft Tube Deck - Phase 3 (2025) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  |  | 855 |  |  |  | 855 | 855 | 0 | Yes | 6 |  | 855 | 6.1001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Rewedge Stator (2025-2026) - Hinds Lake | [5 empty] | $1 Million to $5 Million |  |  | 1500 | 750 |  |  | 2250 | 2250 | 750 | Yes | 6 |  | 1500 | 6.2002 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Annunciator Panel (2025-2026) Upper Salmon | [5 empty] | Under $750,000 |  |  | 150 | 200 |  |  | 350 | 350 | 200 | No | 6 |  | 150 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Replace Diesel/Office/SF6 Roofs (2025) - Cat Arm | [5 empty] | Under $750,000 |  |  | 275 |  |  |  | 275 | 275 | 0 | No | 6 |  | 275 | 6.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Rectifier Transformer (2025-2026) - Hinds Lake | [5 empty] | $750,000 to $1 Million |  |  | 510 | 250 |  |  | 760 | 760 | 250 | Yes | 6 |  | 510 | 6.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Multi Year | N |  | Refurbish Spherical Valves Units 1 and 2 (2025) - Cat Arm | [5 empty] | Under $750,000 |  |  | 200 | 350 |  |  | 550 | 550 | 350 | No | 6 |  | 200 | 6.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Emergency Diesel Generator (2025-2026) - Cat Arm | [5 empty] | Under $750,000 |  |  | 50 | 170 |  |  | 220 | 220 | 170 | No | 6 |  | 50 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Cooling Water Pumps (2025-2026) - Cat Arm | [5 empty] | Under $750,000 |  |  | 50 | 200 |  |  | 250 | 250 | 200 | No | 6 |  | 50 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Refurbish Needle Valve Assembly Unit 2 and Purchase Spare Needle (2025-2026) - Cat Arm | [5 empty] | Under $750,000 |  |  | 100 | 600 |  |  | 700 | 700 | 600 | No | 6 |  | 100 | 6.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Refurbish Unit Control Panels Unit 2 (2025-2026) - Cat Arm | [5 empty] | Under $750,000 |  |  | 100 | 570 |  |  | 670 | 670 | 570 | No | 6 |  | 100 | 6.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Install Dynamic Air Gap Monitoring System (2025-2026) - Hinds Lake | [5 empty] | Under $750,000 |  |  | 100 | 403 |  |  | 503 | 503 | 403 | No | 6 |  | 100 | 6.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Stabilize Powerhouse Slope - Phase 2 (2025) - Cat Arm | [5 empty] | Under $750,000 |  |  | 242.3 |  |  |  | 242.3 | 242.3 | 0 | No | 6 |  | 242.3 | 6.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Replace Flow Measuring Devices Units 1 to 7 (2025) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  | 349.6 |  |  |  | 349.6 | 349.6 | 0 | No | 6 |  | 349.6 | 6.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Install Remote Fuel Monitoring on Gasoline Fuel Tank (2025-2026) - Granite Canal | [5 empty] | Under $750,000 |  |  | 150 | 100 |  |  | 250 | 250 | 100 | No | 6 |  | 150 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Station Service Transformer 1 (2025-2026) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  | 200 | 100 |  |  | 300 | 300 | 100 | No | 6 |  | 200 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Install Asset Health Monitoring System (2025-2026) - Cat Arm | [5 empty] | Under $750,000 |  |  | 150 | 150 |  |  | 300 | 300 | 150 | No | 6 |  | 150 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Intake 4 Level II Condition Assessment (2025) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  | 400 |  |  |  | 400 | 400 | 0 | No | 6 |  | 400 | 6.1 | Yes |  |  | changed from refurbish to replace based on scope.
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Refurbish Intake 2 (2025-2026) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  |  | 500 | 2000 |  |  | 2500 | 2500 | 2000 | Yes | 6 |  | 500 | 6.2002 | Yes |  |  |  | CANCELLED in 2023 CBA Prep
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Unit Annunciator (2025-2026) - Hinds Lake | [5 empty] | Under $750,000 |  |  | 150 | 240 |  |  | 390 | 390 | 240 | No | 6 |  | 150 | 6.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Unit 1 & 2 Spherical Valve Overhaul (2025) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  |  | 750 |  |  |  | 750 | 750 | 0 | Yes | 6 |  | 750 | 6.1001 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Thermal In-Service Failures (2025) | [5 empty] | $1 Million to $5 Million |  |  | 3450 |  |  |  | 3450 | 3450 | 0 | Yes | 6 |  | 3450 | 6.1003 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Turbine and Valve Overhaul - Unit 3 (2025) - Holyrood | [5 empty] | Over $5 Million |  |  | 11444.7 |  |  |  | 11444.7 | 11444.7 | 0 | Yes | 6 |  | 11444.7 | 6.1011 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Boiler Condition Assessment and Miscellaneous Upgrades (2025) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  | 3750 |  |  |  | 3750 | 3750 | 0 | Yes | 6 |  | 3750 | 6.1004 | Yes |  |  | OT
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Major Pump Overhaul (2025) - Holyrood | [5 empty] | Under $750,000 |  |  | 350 |  |  |  | 350 | 350 | 0 | No | 6 |  | 350 | 6.1 | Yes |  |  | OT
Generation | Thermal Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Refurbish Stage I & II Cooling Water Pumphouses (2025-2026) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  | 670 | 700 |  |  | 1370 | 1370 | 700 | Yes | 6 |  | 670 | 6.2001 | Yes |  |  | OT but implemented by IS
Generation | Thermal Plant | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Marine Terminal Upgrades (2025) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  | 200 | 800 |  |  | 1000 | 1000 | 800 | Yes | 6 |  | 200 | 6.2001 | Yes |  |  | OT but implemented by IS
Generation | Gas Turbines | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Gas Turbine In-Service Failures (2025) | [5 empty] | Under $750,000 |  |  | 376 |  |  |  | 376 | 376 | 0 | No | 6 |  | 376 | 6.1 | Yes |  |  | OT (may not be any IT upgrades, may require name change)
Generation | Gas Turbines | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Inspect Fuel Tanks (2025) - Hardwoods Gas Turbine | [5 empty] | Under $750,000 |  |  | 682 |  |  |  | 682 | 682 | 0 | No | 6 |  | 682 | 6.1001 | Yes
Generation | Gas Turbines | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Install Secondary Station Service Supply (2025-2026) - Holyrood Gas Turbine | [5 empty] | Under $750,000 |  |  | 50 | 250 |  |  | 300 | 300 | 250 | No | 6 |  | 50 | 6.2 | Yes |  |  |  | changed by Shane LaCour, was $598.3
Generation | Gas Turbines | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Inspect Fuel Tanks (2025-2026) - Happy Valley Gas Turbine | [5 empty] | Under $750,000 |  |  | 100 | 500 |  |  | 600 | 600 | 500 | No | 6 |  | 100 | 6.2001 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Upgrade Cooling (2025-2026) - Hardwoods Gas Turbine | [5 empty] | $1 Million to $5 Million |  |  | 200 | 800 |  |  | 1000 | 1000 | 800 | Yes | 6 |  | 200 | 6.2001 | Yes |  |  | consider turning this into misc upgrades, or just keep as placeholder for 5 year plan and remove this year?
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) - Thermal Plants | [5 empty] | Under $750,000 |  |  | 50 |  |  |  | 50 | 50 | 0 | No | 6 |  | 50 | 6.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) - Gas Turbines | [5 empty] | Under $750,000 |  |  | 20 |  |  |  | 20 | 20 | 0 | No | 6 |  | 20 | 6.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) - Hydraulic Plants | [5 empty] | Under $750,000 |  |  | 100 |  |  |  | 100 | 100 | 0 | No | 6 |  | 100 | 6.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Renew Circuit Breakers (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 531.8 | 1709.6 |  |  | 2241.4 | 2241.4 | 1709.6 | Yes | 6 |  | 531.8 | 6.2002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Terminal Station In-Service Failures (2025) | [5 empty] | $1 Million to $5 Million |  |  | 1387.1 |  |  |  | 1387.1 | 1387.1 | 0 | Yes | 6 |  | 1387.1 | 6.1001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Instrument Transformers (2025-2026) | [5 empty] | Under $750,000 |  |  | 420 | 280 |  |  | 700 | 700 | 280 | No | 6 |  | 420 | 6.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Protective Relays (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 1250 | 2250 |  |  | 3500 | 3500 | 2250 | Yes | 6 |  | 1250 | 6.2004 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Disconnects (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 439.2 | 815.7 |  |  | 1254.9 | 1254.9 | 815.7 | Yes | 6 |  | 439.2 | 6.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Terminal Station Battery Banks and Chargers (2025-2026) | [5 empty] | Under $750,000 |  |  | 210 | 140 |  |  | 350 | 350 | 140 | No | 6 |  | 210 | 6.2 | Yes |  |  |  | MOVED from 2024 to 2023 in 2022 CBA prep (alignment for PM9), but now back to 2024 based on corporate strategy not reliability.
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Upgrade Power Transformers (2025–2026) | [5 empty] | $1 Million to $5 Million |  |  | 114 | 2599 |  |  | 2713 | 2713 | 2599 | Yes | 6 |  | 114 | 6.2003 | Yes |  |  |  | DEFERRED to 2024 from 2023
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N | P627 | Upgrade Terminal Station for Mobile Substation (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 147.7 | 1105 |  |  | 1252.7 | 1252.7 | 1105 | Yes | 6 |  | 147.7 | 6.2001 | Yes |  |  |  | DEFERRED from 2023 to 2024 in 2023 CBA prep
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Replace SC1/SC2 Overhead Crane (2025-2026) - Wabush Terminal Station | [5 empty] | Under $750,000 |  |  | 120 | 340 |  |  | 460 | 460 | 340 | No | 6 |  | 120 | 6.2 | Yes |  |  | (ditching, culverts, surface) | DEFERRED from 2022 to 2023 in 2022 CBA prep, the DEFERRED again to determine best course of action
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Install Fire Barriers between T10 and T12, T10 and T11 (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 220.4 | 1108.6 |  |  | 1329 | 1329 | 1108.6 | Yes | 6 |  | 220.4 | 6.2001 | Yes |  |  |  | MOVED from 2024 to 2023 in 2022 CBA prep, then back to 2024 in 2023 CBA prep
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Telecontrol Building and Upgrade Equipment (2025-2026) - Daniel's Harbour | [5 empty] | $1 Million to $5 Million |  |  | 408.7 | 1505.2 |  |  | 1913.9 | 1913.9 | 1505.2 | Yes | 6 |  | 408.7 | 6.2002 | Yes |  |  |  | DEFERRED from 2023 to 2024 in 2023 CBA prep
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Construct Fire Separation Walls between Transformers (2025-2026) | [5 empty] | $750,000 to $1 Million |  |  | 54.8 | 773.9 |  |  | 828.7 | 828.7 | 773.9 | Yes | 6 |  | 54.8 | 6.2001 | Yes |  |  |  | DEFERRED from 2023 to 2024 in 2023 CBA prep
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Upgrade Data Alarm Systems (2025-2026) - Hardwoods | [5 empty] | Under $750,000 |  |  | 120 | 180 |  |  | 300 | 300 | 180 | No | 6 |  | 120 | 6.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Circuit Breaker Reclosing Controller (2025-2026) - Sunnyside | [5 empty] | $750,000 to $1 Million |  |  | 54 | 710 |  |  | 764 | 764 | 710 | Yes | 6 |  | 54 | 6.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Install Fire Protection in 230 kV Stations (2025-2026) - Come By Chance | [5 empty] | Under $750,000 |  |  | 68 | 616 |  |  | 684 | 684 | 616 | No | 6 |  | 68 | 6.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Refurbish Control Building (2025-2026) | [5 empty] | Under $750,000 |  |  | 125.1 | 310.4 |  |  | 435.5 | 435.5 | 310.4 | No | 6 |  | 125.1 | 6.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Upgrade Station Access Road (2025) - Buchans, Western Avalon, Sunnyside, Deer Lake | [5 empty] | Under $750,000 |  |  | 200 |  |  |  | 200 | 200 | 0 | No | 6 |  | 200 | 6.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Install New Station Service Feed (2025-2026) - Berry Hill | [5 empty] | Under $750,000 |  |  | 50 | 150 |  |  | 200 | 200 | 150 | No | 6 |  | 50 | 6.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Synchronous Condenser 2 Major Inspection (2025-2026) - Wabush Terminal Station | [5 empty] | Under $750,000 |  |  | 40 | 240 |  |  | 280 | 280 | 240 | No | 6 |  | 40 | 6.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Switchgear (2025-2026) - Grand Falls Terminal Station | [5 empty] | Under $750,000 |  |  | 50 | 300 |  |  | 350 | 350 | 300 | No | 6 |  | 50 | 6.2 | Yes |  |  |  | DEFERRED from 2022 to 2024 in 2022 CBA prep
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Switchgear Synchronous Condensers 1 and 2 (2025-2026) - Wabush Terminal Station | [5 empty] | $750,000 to $1 Million |  |  | 50 | 700 |  |  | 750 | 750 | 700 | Yes | 6 |  | 50 | 6.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Upgrade Terminal Station for Mobile Substation (2025-2026) | [5 empty] | Under $750,000 |  |  | 60 | 400 |  |  | 460 | 460 | 0 | No | 6 |  | 60 | 6.2 | Yes |  |  | was 100 in 2024 and 100 in 2025 | CANCELLED in 2023 CBA prep was in 2024-2025, because of CA in 2023
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Upgrade Transformer Paralleling (2025-2026) - Stoney Brook | [5 empty] | Under $750,000 |  |  | 36 | 54 |  |  | 90 | 90 | 0 | No | 6 |  | 36 | 6.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Install Breaker Failure Protection (2025–2026) - Holyrood TS | [5 empty] | Under $750,000 |  |  | 135 | 315 |  |  | 450 | 450 | 315 | No | 6 |  | 135 | 6.2 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Transmission In-Service Failures (2025) | [5 empty] | Under $750,000 |  |  | 162 |  |  |  | 162 | 162 | 0 | No | 6 |  | 162 | 6.1 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Wood Pole Line Management (2025) | [5 empty] | $1 Million to $5 Million |  |  | 2446 |  |  |  | 2446 | 2446 | 0 | Yes | 6 |  | 2446 | 6.1002 | Yes
Transmission and Rural Operations | Transmission | Project |  |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | TL220 Install Mid Span Poles (2025-2026) | [5 empty] | $750,000 to $1 Million |  |  | 150 | 600 |  |  | 750 | 750 | 600 | Yes | 6 |  | 150 | 6.2001 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Access | 2025 |  | 2025 | Single Year | N |  | Provide Service Extensions (2025) | [5 empty] | $1 Million to $5 Million |  |  | 4369 |  |  |  | 4369 | 4369 | 0 | Yes | 6 |  | 4369 | 6.1004 | Yes |  |  |  | MOVED from 2023 to 2024
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Distribution System In-Service Failures, Miscellaneous Upgrades, and Street Lights (2025) | [5 empty] | $1 Million to $5 Million |  |  | 4454 |  |  |  | 4454 | 4454 | 0 | Yes | 6 |  | 4454 | 6.1004 | Yes |  |  | was 670 and 400 | DEFERRED from 2023 to date TBD
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Upgrade Worst-Performing Distribution Feeders (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 480.3 | 2719.95 |  |  | 3200.25 | 3200.25 | 2719.95 | Yes | 6 |  | 480.3 | 6.2003 | Yes |  |  | combined with Replace Stage I 4160 V ac Breakers - Holyrood which was 200 in 2023 and 700 in 2024, was 498.9 in 2023 and 5666.8 in 2024 | DEFERRED from 2023 to date 2024
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Renew Distribution Feeders (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 1287.3 | 1245.1 |  |  | 2532.4 | 2532.4 | 1245.1 | Yes | 6 |  | 1287.3 | 6.2003 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2025 | 2025 |  | Multi Year | N |  | Distribution Equipment SCADA Additions (2025-2026) | [5 empty] | Under $750,000 |  |  | 30 | 270 |  |  | 300 | 300 | 270 | No | 6 |  | 30 | 6.2 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | System Growth | 2025 |  | 2025 | Single Year | N |  | Additions for Load (2025) - Distribution System | [5 empty] | $1 Million to $5 Million |  |  | 1000 |  |  |  | 1000 | 1000 | 0 | Yes | 6 |  | 1000 | 6.1001 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace T1 Burgeo Substation (2025-2026) | [5 empty] | $750,000 to $1 Million |  |  | 200 | 600 |  |  | 800 | 800 | 600 | Yes | 6 |  | 200 | 6.2001 | Yes
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Diesel Genset Unit 2067 (2025) - Grey River | [5 empty] | $1 Million to $5 Million |  |  | 200 | 1400 |  |  | 1600 | 1600 | 1400 | Yes | 6 |  | 200 | 6.2002 | Yes
Transmission and Rural Operations | Generation | Program | Roll Up |  | Renewal | 2025 | 2025 |  | Multi Year | N |  | Replace Diesel Gensets (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 200 | 1400 |  |  | 1600 | 1600 | 1400 | Yes | 6 |  | 200 | 6.2002 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Overhaul Diesel Units (2025) | [5 empty] | $1 Million to $5 Million |  |  | 1500 |  |  |  | 1500 | 1500 | 0 | Yes | 6 |  | 1500 | 6.1002 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Diesel In-Service Failures (2025) | [5 empty] | Under $750,000 |  |  | 489.5 |  |  |  | 489.5 | 489.5 | 0 | No | 6 |  | 489.5 | 6.1 | Yes
Transmission and Rural Operations | Generation | Project |  |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Inspect Fuel Storage Tanks (2025) - MacCallum | [5 empty] | $1 Million to $5 Million |  |  | 1000 |  |  |  | 1000 | 1000 | 0 | Yes | 6 |  | 1000 | 6.1001 | Yes
Transmission and Rural Operations | Generation | Project |  |  | System Growth | 2025 |  | 2025 | Single Year | N |  | Additions for Load Growth - Isolated Generation Stations (2025) | [5 empty] | Under $750,000 |  |  | 650 |  |  |  | 650 | 650 | 0 | No | 6 |  | 650 | 6.1001 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N | P655 | Upgrade Line Depots (2025-2027) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  |  | 320.4 | 1514.7 | 1400.6 |  | 3235.7 | 3235.7 | 2915.3 | Yes | 6 |  | 320.4 | 6.3003 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Resurface Parking Lots and Roads (2024) - Bishop's Falls | [5 empty] | Under $750,000 |  |  | 150 |  |  |  | 150 | 150 | 0 | No | 6 |  | 150 | 6.1 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Construct Storage Building (2025-2026) - Springdale | [5 empty] | $750,000 to $1 Million |  |  | 135 | 730 |  |  | 865 | 865 | 730 | Yes | 6 |  | 135 | 6.2001 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Upgrade Outside Property (2025) - Deer Lake | [5 empty] | Under $750,000 |  |  | 129 |  |  |  | 129 | 129 | 0 | No | 6 |  | 129 | 6.1 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Upgrade Property (2025) - Bishop's Falls, Whitbourne, St. Anthony | [5 empty] | Under $750,000 |  |  | 370 |  |  |  | 370 | 370 | 0 | No | 6 |  | 370 | 6.1 | Yes
Transmission and Rural Operations | Metering | Program | Standalone |  | Access | 2025 |  | 2025 | Single Year | N |  | Purchase Meters and Metering Equipment (2025) | [5 empty] | Under $750,000 |  |  | 475.5 |  |  |  | 475.5 | 475.5 | 0 | No | 6 |  | 475.5 | 6.1 | Yes |  |  |  | DEFERRED to 2024 in 2023 CBA prep
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) - Central Region | [5 empty] | Under $750,000 |  |  | 180 |  |  |  | 180 | 180 | 0 | No | 6 |  | 180 | 6.1 | Yes |  |  | needs stronger justification. | DEFERRED from 2022 to 2023 in 2022 CBA prep, then again to 2024 in 2023 CBA prep.
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) - Northern Region | [5 empty] | Under $750,000 |  |  | 120 |  |  |  | 120 | 120 | 0 | No | 6 |  | 120 | 6.1 | Yes |  |  |  | DEFERRED from 2023 to 2024 in 2023 CBA prep
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) - Labrador Region | [5 empty] | Under $750,000 |  |  | 100 |  |  |  | 100 | 100 | 0 | No | 6 |  | 100 | 6.1 | Yes |  |  |  | DEFERED from 2023 to 2024 to provide more notice to Vale on specifically assigned change
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Replace Off Road Heavy-Duty Equipment (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 500 | 500 |  |  | 1000 | 1000 | 500 | Yes | 6 |  | 500 | 6.2001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Perform Software Upgrades and Minor Enhancements (2025) | [5 empty] | Under $750,000 |  |  | 705 |  |  |  | 705 | 705 | 0 | No | 6 |  | 705 | 6.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Update Cyber Security Infrastructure (2025) | [5 empty] | Under $750,000 |  |  | 225 |  |  |  | 225 | 225 | 0 | No | 6 |  | 225 | 6.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Personal Computers (2025) | [5 empty] | Under $750,000 |  |  | 635.8 |  |  |  | 635.8 | 635.8 | 0 | No | 6 |  | 635.8 | 6.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Replace Peripheral Infrastructure (2025) | [5 empty] | Under $750,000 |  |  | 190.4 |  |  |  | 190.4 | 190.4 | 0 | No | 6 |  | 190.4 | 6.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Upgrade Core OT Infrastructure (2025) | [5 empty] | Under $750,000 |  |  | 375 |  |  |  | 375 | 375 | 0 | No | 6 |  | 375 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2025) | [5 empty] | Under $750,000 |  |  | 49.7 |  |  |  | 49.7 | 49.7 | 0 | No | 6 |  | 49.7 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Minor Telecommunications Enhancements (2025) | [5 empty] | Under $750,000 |  |  | 98.8 |  |  |  | 98.8 | 98.8 | 0 | No | 6 |  | 98.8 | 6.1 | Yes |  |  |  | DEFERRED from 2022 to 2024 in 2022 CBA prep
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Replace Network Communications Equipment (2025) | [5 empty] | Under $750,000 |  |  | 215.5 |  |  |  | 215.5 | 215.5 | 0 | No | 6 |  | 215.5 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Mobile Devices (2025) | [5 empty] | Under $750,000 |  |  | 132 |  |  |  | 132 | 132 | 0 | No | 6 |  | 132 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Upgrade Remote Terminal Units (2025) | [5 empty] | Under $750,000 |  |  | 168 |  |  |  | 168 | 168 | 0 | No | 6 |  | 168 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Site Physical Security Program (2025) | [5 empty] | Under $750,000 |  |  | 108 |  |  |  | 108 | 108 | 0 | No | 6 |  | 108 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Replace 48 V Battery Banks and Chargers (2025) | [5 empty] | Under $750,000 |  |  | 428.3 |  |  |  | 428.3 | 428.3 | 0 | No | 6 |  | 428.3 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2025 |  | 2025 | Single Year | N |  | Telecommunications Tower Condition Management (2025) | [5 empty] | Under $750,000 |  |  | 93 |  |  |  | 93 | 93 | 0 | No | 6 |  | 93 | 6.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Telecommunications In-Service Failure (2025) | [5 empty] | Under $750,000 |  |  | 93 |  |  |  | 93 | 93 | 0 | No | 6 |  | 93 | 6.1 | Yes |  |  |  | DEFERRED from 2023 to 2024 in 2023 CBA prep
General Properties | Telecontrol | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Replace East Coast to Central Interconnect Microwave Radios (2025-2027) | [5 empty] | Under $750,000 |  |  | 100 | 400 | 150 |  | 650 | 650 | 550 | No | 6 |  | 100 | 6.3001 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Replace Uninterruptible Power Supply Batteries (2025) - Hydro Place | [5 empty] | Under $750,000 |  |  | 75 |  |  |  | 75 | 75 | 0 | No | 6 |  | 75 | 6.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Refurbish Office Energy Efficiency and HVAC Systems (2025-2026) - Deer Lake | [5 empty] | Under $750,000 |  |  | 75 | 100 |  |  | 175 | 175 | 100 | No | 6 |  | 75 | 6.2 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Refurbish Meteorological Sites (2025) | [5 empty] | Under $750,000 |  |  | 100 | 100 |  |  | 200 | 200 | 100 | No | 6 |  | 100 | 6.2 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Install CCTV Systems (2025) | [5 empty] | Under $750,000 |  |  | 321.3 |  |  |  | 321.3 | 321.3 | 0 | No | 6 |  | 321.3 | 6.1 | Yes |  |  |  | DEFERRED to 2024 from 2023
General Properties | Transportation | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Replace Mobile Equipment (2025) | [5 empty] | Under $750,000 |  |  | 600 |  |  |  | 600 | 600 | 0 | No | 6 |  | 600 | 6.1001 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Replace Light- and Heavy-Duty Vehicles (2025-2026) | [5 empty] | $1 Million to $5 Million |  |  | 2000 | 2000 |  |  | 4000 | 4000 | 2000 | Yes | 6 |  | 2000 | 6.2004 | Yes
General Properties | Administration | Program | Standalone |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Purchase Furniture & Equipment Less Than $50,000 (2025) | [5 empty] | Under $750,000 |  |  | 67.3 |  |  |  | 67.3 | 67.3 | 0 | No | 6 |  | 67.3 | 6.1 | Yes
General Properties | Administration | Program | Standalone |  | Service Enhancement | 2025 |  | 2025 | Single Year | N |  | Remove Safety Hazards (2025) | [5 empty] | Under $750,000 |  |  | 208 |  |  |  | 208 | 208 | 0 | No | 6 |  | 208 | 6.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2025 |  | 2025 | Single Year | N |  | Security Improvements Less Than $50,000 (2025) | [5 empty] | Under $750,000 |  |  | 37 |  |  |  | 37 | 37 |  | No | 6 |  | 37 | 6.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2025 | 2025 |  | Multi Year | N |  | Barrier Free Improvements - Washrooms (2025-2026) | [5 empty] | $750,000 to $1 Million |  |  | 428 | 346.5 |  |  | 774.5 | 774.5 |  | Yes | 6 |  | 428 | 6.2001 | Yes |  |  |  | DEFERRED to 2024 from 2023 in the 2023 CBA
Allowance for Unforeseen Items |  | Program | Standalone |  | Allowance for Unforeseen | 2025 |  | 2025 | Single Year | N |  | Allowance for Unforeseen Items (2025) | [5 empty] | $1 Million to $5 Million |  |  | 1000 |  |  |  | 1000 | 1000 | 0 | Yes | 6 |  | 1000 | 6.1001 | Yes
Generation | Hydraulic Plant | Major Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | Y |  | Penstock Life Extension - Phase 2 (2026-2028) | [5 empty] | Over $5 Million |  |  |  | 1900 | 8200 | 10000 | 20100 | 20100 | 18200 | Yes | 5 |  | 1900 | 5.302 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Unit 7 (2026) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  |  |  | 750 |  |  | 750 | 750 | 0 | Yes | 5 |  | 750 | 5.1001 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Unit 1 (2026) - Hinds Lake | [5 empty] | Under $750,000 |  |  |  | 325 |  |  | 325 | 325 | 0 | No | 5 |  | 325 | 5.1 | Yes |  |  |  | DEFERRED to 2024 from 2023
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Unit 2 (2026) - Cat Arm | [5 empty] | Under $750,000 |  |  |  | 350 |  |  | 350 | 350 | 0 | No | 5 |  | 350 | 5.1 | Yes
Generation | Hydraulic Plant | Program | Roll Up |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Hydraulic Units (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 1425 |  |  | 1425 | 1425 | 0 | Yes | 5 |  | 1425 | 5.1001 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Hydraulic In-Service Failures (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 1604 |  |  | 1604 | 1604 | 0 | Yes | 5 |  | 1604 | 5.1002 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Penstock Level II Condition Assessment (2026) - Hind's Lake | [5 empty] | Under $750,000 |  |  |  | 200 |  |  | 200 | 200 | 0 | No | 5 |  | 200 | 5.1 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Penstock Level II Condition Assessment- Steel Liner (2026) - Cat Arm | [5 empty] | Under $750,000 |  |  |  | 200 |  |  | 200 | 200 | 0 | No | 5 |  | 200 | 5.1 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Resurface Access Road and Intake (2026-2027) Paradise River | [5 empty] | $750,000 to $1 Million |  |  |  | 100 | 861.1 |  | 961.1 | 961.1 | 961.1 | Yes | 5 |  | 100 | 5.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Replace Site Domestic Water System (2026-2027) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  |  |  | 50 | 750 |  | 800 | 800 | 800 | Yes | 5 |  | 50 | 5.2001 | Yes |  |  | now on a two year cycle so 2023 was removed | now on a 2 year cycle, so not needed in 2023
Generation | Hydraulic Plant | Project |  |  | General Plant | 2026 |  | 2026 | Multi Year | N |  | Replace Powerhouse Septic System (2026-2027) - Hinds Lake | [5 empty] | Under $750,000 |  |  |  | 50 | 227.3 |  | 277.3 | 277.3 | 227.3 | No | 5 |  | 50 | 5.2 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Replace Walkway to Toe of Dam (2026) - Paradise River | [5 empty] | Under $750,000 |  |  |  | 80 |  |  | 80 | 80 | 0 | No | 5 |  | 80 | 5.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Refurbish Rip Rap Material on Pudops Dam MD-2 (2026) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  |  |  | 800 |  |  | 800 | 800 | 0 | Yes | 5 |  | 800 | 5.1001 | Yes
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | Upgrade Excitation System (2026-2027) - Paradise River | [5 empty] | Under $750,000 |  |  |  | 250 | 250 |  | 500 | 500 | 250 | No | 5 |  | 250 | 5.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace Burnt Dam Diesel Fuel Tanks 2 and 3 (2026-2027) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  |  | 50 | 250 |  | 300 | 300 | 250 | No | 5 |  | 50 | 5.2 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Replace Burnt Dam Septic System (2026-2027) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  |  | 50 | 125 |  | 175 | 175 | 125 | No | 5 |  | 50 | 5.2 | Yes |  |  |  | Deferred from 2023 to 2024 as per Shane Lacour Nov 22
Generation | Hydraulic Plant | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Refurbish Spherical Valves Unit 5 (2026-2027) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  |  | 100 | 275 |  | 375 | 375 |  | No | 5 |  | 100 | 5.2 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Level II Condition Assessment Powerhouse 2 Roof (2026) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  |  | 100 |  |  |  | 100 |  | No | 5 |  | 100 | 5.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | North Salmon Spillway Level II Condition Assessment (2026) - Upper Salmon | [5 empty] | Under $750,000 |  |  |  | 400 |  |  |  | 400 |  | No | 5 |  | 400 | 5.1 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Thermal In-Service Failures (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 3528 |  |  | 3528 | 3528 | 0 | Yes | 5 |  | 3528 | 5.1004 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Major Pump Overhaul (Unit 1 WBFP, Unit 1 ECWP, Unit 1 SCEP, Unit 2 SCEP, Unit 3 WBFP) | [5 empty] | $1 Million to $5 Million |  |  |  | 1400 |  |  | 1400 | 1400 | 0 | Yes | 5 |  | 1400 | 5.1001 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Boiler Condition Assessment and Miscellaneous Upgrades (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 3500 |  |  | 3500 | 3500 | 0 | Yes | 5 |  | 3500 | 5.1003 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Unit 2 Turbine Valves | [5 empty] | $1 Million to $5 Million |  |  |  | 3873 |  |  | 3873 | 3873 | 0 | Yes | 5 |  | 3873 | 5.1004 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Unit 2 Generator | [5 empty] | $1 Million to $5 Million |  |  |  | 1839 |  |  | 1839 | 1839 | 0 | Yes | 5 |  | 1839 | 5.1002 | Yes |  |  | Fomerly Upgrade Site Facilities
Generation | Thermal Plant | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Replace Parts of Unit 3: 129 Vdc Battery Chargers, Batteries, Panels, and Breakers (2026) - Holyrood | [5 empty] | $750,000 to $1 Million |  |  |  | 750 |  |  | 750 | 750 | 0 | Yes | 5 |  | 750 | 5.1001 | Yes |  |  | Fomerly Replace Radomes
Generation | Thermal Plant | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Upgrade Cranes and Hoists (2026-2027) - Holyrood | [5 empty] | Under $750,000 |  |  |  | 200 | 300 |  | 500 | 500 | 300 | No | 5 |  | 200 | 5.2001 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Inspect Stacks (2026) - Holyrood | [5 empty] | Under $750,000 |  |  |  | 250 |  |  | 250 | 250 | 0 | No | 5 |  | 250 | 5.1 | Yes
Generation | Thermal Plant | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Upgrade Synchronous Condenser Building (2026-2027) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  | 200 | 1000 |  | 1200 | 1200 | 1000 | Yes | 5 |  | 200 | 5.2001 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Upgrade Synchronous Condenser Building (2026-2027) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  | 200 | 4600 |  | 4800 | 4800 | 4600 | Yes | 5 |  | 200 | 5.2005 | Yes
Generation | Thermal Plant | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Install Plant Heating (2028-2029) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  |  | 519 | 2500 | 3019 | 3019 | 3019 | Yes | 5 |  | 519 | 5.2003 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Upgrade Water Treatment Plant and Waste Water Treatment Plant - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  | 1000 |  |  | 1000 | 1000 | 0 | Yes | 5 |  | 1000 | 5.1001 | Yes
Generation | Gas Turbines | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Gas Turbine In-Service Failures (2026) | [5 empty] | Under $750,000 |  |  |  | 395 |  |  | 395 | 395 | 0 | No | 5 |  | 395 | 5.1 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Refurbish Air Intake (2026) - Happy Valley Gas Turbine | [5 empty] | Under $750,000 |  |  |  | 600 |  |  | 600 | 600 | 0 | No | 5 |  | 600 | 5.1001 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Major Inspection Gas Turbine (2026-2027) - Holyrood Gas Turbine | [5 empty] | Over $5 Million |  |  |  | 7500 | 7500 |  | 15000 | 15000 | 7500 | Yes | 5 |  | 7500 | 5.2015 | Yes |  |  |  | MOVED from 2023 to 2024 in 2022 CBA prep, then 2025 in 2023 CBA prep
Generation | Gas Turbines | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Replace DC Fuel Pumps | [5 empty] | Under $750,000 |  |  |  | 50 |  |  | 50 | 50 | 0 | No | 5 |  | 50 | 5.1 | Yes |  |  |  | MOVED from 2024 to 2023 in 2022 CBA prep, then from 2023 to 2025 in 2023 CBA prep
Generation | Gas Turbines | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Replace Air Dryer | [5 empty] | Under $750,000 |  |  |  | 50 |  |  | 50 | 50 | 0 | No | 5 |  | 50 | 5.1 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Replace Batteries | [5 empty] | Under $750,000 |  |  |  | 75 |  |  | 75 | 75 | 0 | No | 5 |  | 75 | 5.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) - Thermal Plants | [5 empty] | Under $750,000 |  |  |  | 50 |  |  | 50 | 50 | 0 | No | 5 |  | 50 | 5.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) - Gas Turbines | [5 empty] | Under $750,000 |  |  |  | 20 |  |  | 20 | 20 | 0 | No | 5 |  | 20 | 5.1 | Yes
Generation | Tools and Equipment | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) - Hydraulic Plants | [5 empty] | Under $750,000 |  |  |  | 100 |  |  |  | 100 |  | No | 5 |  | 100 | 5.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Terminal Station In-Service Failures (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 1480.04 |  |  | 1480.04 | 1480.04 | 0 | Yes | 5 |  | 1480.04 | 5.1001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Renew Circuit Breakers (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 406 | 794 |  | 1200 | 1200 | 794 | Yes | 5 |  | 406 | 5.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace Instrument Transformers (2026-2027) | [5 empty] | Under $750,000 |  |  |  | 290 | 200 |  | 490 | 490 | 200 | No | 5 |  | 290 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace Protective Relays (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 850 | 1350 |  | 2200 | 2200 | 1350 | Yes | 5 |  | 850 | 5.2002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace Disconnects (2026-2027) | [5 empty] | $750,000 to $1 Million |  |  |  | 348.3 | 646.8 |  | 995.1 | 995.1 | 646.8 | Yes | 5 |  | 348.3 | 5.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Upgrade Power Transformers (2026–2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 89 | 1837 |  | 1926 | 1926 | 1837 | Yes | 5 |  | 89 | 5.2002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace Terminal Station Battery Banks and Chargers (2026-2027) | [5 empty] | Under $750,000 |  |  |  | 190 | 130 |  | 320 | 320 | 130 | No | 5 |  | 190 | 5.2 | Yes |  |  |  | MOVED from 2022 to 2025 in 2022 CBA prep
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | Install Fire Barriers between Substation and T1, T2, and T3 (2026-2027) | [5 empty] | $750,000 to $1 Million |  |  |  | 39.1 | 731.5 |  | 770.6 | 770.6 | 731.5 | Yes | 5 |  | 39.1 | 5.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Refurbish Control Building (2026–2027) | [5 empty] | Under $750,000 |  |  |  | 124.9 | 310 |  | 434.9 | 434.9 | 310 | No | 5 |  | 124.9 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Upgrade Data Alarm System (2026–2027) - Springdale and Indian River Terminal Stations | [5 empty] | Under $750,000 |  |  |  | 50 | 80 |  | 130 | 130 | 80 | No | 5 |  | 50 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | Upgrade Transformer Paralleling (2026-2027) - Sunnyside | [5 empty] | Under $750,000 |  |  |  | 36 | 54 |  | 90 | 90 | 54 | No | 5 |  | 36 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace Circuit Breaker Reclosing Controllers (2026-2027) - Holyrood | [5 empty] | Under $750,000 |  |  |  | 54 | 71 |  | 125 | 125 | 71 | No | 5 |  | 54 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Install Fire Protection in 230 kV Stations (2026-2027) - Bottom Brook | [5 empty] | Under $750,000 |  |  |  | 68 | 616 |  | 684 | 684 | 616 | No | 5 |  | 68 | 5.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | Upgrade Terminal Station for Mobile Substation (2026–2027) - St. Anthony Diesel | [5 empty] | Under $750,000 |  |  |  | 60 | 400 |  | 460 | 460 | 400 | No | 5 |  | 60 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Synchronous Condenser 1 Major Inspection (2026-2027) - Wabush Terminal Station | [5 empty] | Under $750,000 |  |  |  | 40 | 240 |  | 280 | 280 | 240 | No | 5 |  | 40 | 5.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Install Breaker Failure Protection (2026-2027) - Hardwoods | [5 empty] | Under $750,000 |  |  |  | 135 | 315 |  | 450 | 450 | 315 | No | 5 |  | 135 | 5.2 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Transmission In-Service Failures (2026) | [5 empty] | Under $750,000 |  |  |  | 166 |  |  | 166 | 166 | 0 | No | 5 |  | 166 | 5.1 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Wood Pole Line Management (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 4386 |  |  | 4386 | 4386 | 0 | Yes | 5 |  | 4386 | 5.1004 | Yes
Transmission and Rural Operations | Transmission | Project |  |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | TL220 Relocate Section of Line (2026-2027) | [5 empty] | $750,000 to $1 Million |  |  |  | 150 | 600 |  | 750 | 750 | 600 | Yes | 5 |  | 150 | 5.2001 | Yes |  |  |  | MOVED from 2023 to 2025 in 2022 CBA prep
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Steel-Tower Transmission Line Renewal (2026-2032) | [5 empty] | Over $5 Million |  |  |  | 5000 | 24595 | 36233 | 65828 | 65828 | 60828 | Yes | 5 |  | 5000 | 5.3066 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Access | 2026 |  | 2026 | Single Year | N |  | Provide Service Extensions (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 4467 |  |  | 4467 | 4467 | 0 | Yes | 5 |  | 4467 | 5.1004 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Distribution System In-Service Failures, Miscellaneous Upgrades, and Street Lights (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 4565 |  |  | 4565 | 4565 | 0 | Yes | 5 |  | 4565 | 5.1005 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | Upgrade Worst-Performing Distribution Feeders (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 480.3 | 2719.95 |  | 3200.25 | 3200.25 | 2719.95 | Yes | 5 |  | 480.3 | 5.2003 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Renew Distribution Feeders (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 1287.3 | 1245.1 |  | 2532.4 | 2532.4 | 1245.1 | Yes | 5 |  | 1287.3 | 5.2003 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2026 | 2026 |  | Multi Year | N |  | Distribution Equipment SCADA Additions (2026-2027) | [5 empty] | Under $750,000 |  |  |  | 30 | 270 |  | 300 | 300 | 270 | No | 5 |  | 30 | 5.2 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | System Growth | 2026 |  | 2026 | Single Year | N |  | Additions for Load (2026) - Distribution System | [5 empty] | $1 Million to $5 Million |  |  |  | 1000 |  |  | 1000 | 1000 | 0 | Yes | 5 |  | 1000 | 5.1001 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | Renewal | 2026 | 2026 |  | Multi Year | N |  | Replace T2 St. Anthony Diesel Plant Terminal Station (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 500 | 1500 |  | 2000 | 2000 | 1500 | Yes | 5 |  | 500 | 5.2002 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Overhaul Diesel Units (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 1500 |  |  | 1500 | 1500 | 0 | Yes | 5 |  | 1500 | 5.1002 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Diesel In-Service Failures (2026) | [5 empty] | Under $750,000 |  |  |  | 490 |  |  | 490 | 490 | 0 | No | 5 |  | 490 | 5.1 | Yes
Transmission and Rural Operations | Generation | Project |  |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Inspect Fuel Storage Tanks (2026) - Rigolet | [5 empty] | Under $750,000 |  |  |  | 650 |  |  | 650 | 650 | 0 | No | 5 |  | 650 | 5.1001 | Yes
Transmission and Rural Operations | Generation | Project |  |  | System Growth | 2026 |  | 2026 | Single Year | N |  | Additions for Load Growth - Isolated Generation Stations (2026) | [5 empty] | Under $750,000 |  |  |  | 650 |  |  | 650 | 650 | 0 | No | 5 |  | 650 | 5.1001 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Upgrade Property (2026) - Port Saunders, Stephenville, and Happy Valley | [5 empty] | Under $750,000 |  |  |  | 300 |  |  | 300 | 300 | 0 | No | 5 |  | 300 | 5.1 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Replace Sewage System (2026) - Bishop's Falls | [5 empty] | Under $750,000 |  |  |  | 150 |  |  | 150 | 150 | 0 | No | 5 |  | 150 | 5.1 | Yes |  |  |  | MOVED from 2023 to 2025 in 2022 CBA prep
Transmission and Rural Operations | Metering | Program | Standalone |  | Access | 2026 |  | 2026 | Single Year | N |  | Purchase Meters and Metering Equipment (2026) | [5 empty] | Under $750,000 |  |  |  | 625.5 |  |  | 625.5 | 625.5 | 0 | No | 5 |  | 625.5 | 5.1001 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) - Central Region | [5 empty] | Under $750,000 |  |  |  | 180 |  |  | 180 | 180 | 0 | No | 5 |  | 180 | 5.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) - Northern Region | [5 empty] | Under $750,000 |  |  |  | 120 |  |  | 120 | 120 | 0 | No | 5 |  | 120 | 5.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) - Labrador Region | [5 empty] | Under $750,000 |  |  |  | 100 |  |  | 100 | 100 | 0 | No | 5 |  | 100 | 5.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Replace Off Road Heavy-Duty Equipment (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 500 | 500 |  | 1000 | 1000 | 500 | Yes | 5 |  | 500 | 5.2001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Upgrade Energy Management System (2026) - Hydro Place | [5 empty] | Under $750,000 |  |  |  | 355 |  |  | 355 | 355 | 0 | No | 5 |  | 355 | 5.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Perform Software Upgrades and Minor Enhancements (2026) | [5 empty] | Under $750,000 |  |  |  | 625 |  |  | 625 | 625 | 0 | No | 5 |  | 625 | 5.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Update Cyber Security Infrastructure (2026) | [5 empty] | Under $750,000 |  |  |  | 322 |  |  | 322 | 322 | 0 | No | 5 |  | 322 | 5.1 | Yes |  |  |  | MOVED from 2023 to 2025 in 2022 CBA prep
General Properties | Information Systems | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Personal Computers (2026) | [5 empty] | $750,000 to $1 Million |  |  |  | 941.5 |  |  | 941.5 | 941.5 | 0 | Yes | 5 |  | 941.5 | 5.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Replace Peripheral Infrastructure (2026) | [5 empty] | Under $750,000 |  |  |  | 172.4 |  |  | 172.4 | 172.4 | 0 | No | 5 |  | 172.4 | 5.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Upgrade Core OT Infrastructure (2026) | [5 empty] | Under $750,000 |  |  |  | 375 |  |  | 375 | 375 | 0 | No | 5 |  | 375 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2026) | [5 empty] | Under $750,000 |  |  |  | 49.7 |  |  | 49.7 | 49.7 | 0 | No | 5 |  | 49.7 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Mobile Devices (2026) | [5 empty] | Under $750,000 |  |  |  | 202.6 |  |  | 202.6 | 202.6 | 0 | No | 5 |  | 202.6 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Upgrade Remote Terminal Units (2026) | [5 empty] | Under $750,000 |  |  |  | 173 |  |  | 173 | 173 | 0 | No | 5 |  | 173 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Site Physical Security Program (2026) | [5 empty] | Under $750,000 |  |  |  | 112 |  |  | 112 | 112 | 0 | No | 5 |  | 112 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Minor Telecommunications Enhancements (2026) | [5 empty] | Under $750,000 |  |  |  | 101.7 |  |  | 101.7 | 101.7 | 0 | No | 5 |  | 101.7 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Replace Network Communications Equipment (2026) | [5 empty] | Under $750,000 |  |  |  | 222 |  |  | 222 | 222 | 0 | No | 5 |  | 222 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Replace 48 V Battery Banks and Chargers (2026) | [5 empty] | Under $750,000 |  |  |  | 441.1 |  |  | 441.1 | 441.1 | 0 | No | 5 |  | 441.1 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2026 |  | 2026 | Single Year | N |  | Telecommunications Tower Condition Management (2026) | [5 empty] | Under $750,000 |  |  |  | 96 |  |  | 96 | 96 | 0 | No | 5 |  | 96 | 5.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Telecommunications In-Service Failure (2026) | [5 empty] | Under $750,000 |  |  |  | 96 |  |  | 96 | 96 | 0 | No | 5 |  | 96 | 5.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Replace Back-up Generators at Microwave Repeater Sites (2026-2027) | [5 empty] | Under $750,000 |  |  |  | 100 | 50 |  | 150 | 150 | 50 | No | 5 |  | 100 | 5.2 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Install CCTV Systems (2026) | [5 empty] | Under $750,000 |  |  |  | 200 |  |  | 200 | 200 | 0 | No | 5 |  | 200 | 5.1 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Replace Mobile Equipment (2026) | [5 empty] | Under $750,000 |  |  |  | 600 |  |  | 600 | 600 | 0 | No | 5 |  | 600 | 5.1001 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Replace Light- and Heavy-Duty Vehicles (2026-2027) | [5 empty] | $1 Million to $5 Million |  |  |  | 2000 | 2000 |  | 4000 | 4000 | 2000 | Yes | 5 |  | 2000 | 5.2004 | Yes
General Properties | Administration | Program | Standalone |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Purchase Office Equipment Less Than $50,000 (2026) | [5 empty] | Under $750,000 |  |  |  | 68 |  |  | 68 | 68 | 0 | No | 5 |  | 68 | 5.1 | Yes
General Properties | Administration | Program | Standalone |  | Service Enhancement | 2026 |  | 2026 | Single Year | N |  | Remove Safety Hazards (2026) | [5 empty] | Under $750,000 |  |  |  | 213 |  |  | 213 | 213 | 0 | No | 5 |  | 213 | 5.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2026 |  | 2026 | Single Year | N |  | Replace/Upgrade Fire Suppression System (2026) | [5 empty] | Under $750,000 |  |  |  | 508 |  |  | 508 | 508 | 508 | No | 5 |  | 508 | 5.1001 | Yes
General Properties | Administration | Project |  |  | General Plant | 2026 | 2026 |  | Multi Year | N |  | Window Refurbishment/Replacement Program (2026-2028) | [5 empty] | $1 Million to $5 Million |  |  |  | 1041.5 | 1057.5 | 1074 | 3173 | 3173 |  | Yes | 5 |  | 1041.5 | 5.3003 | Yes
Allowance for Unforeseen Items |  | Program | Standalone |  | Allowance for Unforeseen | 2026 |  | 2026 | Single Year | N |  | Allowance for Unforeseen Items (2026) | [5 empty] | $1 Million to $5 Million |  |  |  | 1000 |  |  | 1000 | 1000 | 0 | Yes | 5 |  | 1000 | 5.1001 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Overhaul Unit 5 (2027) - Bay d'Espoir | [5 empty] | Under $750,000 |  |  |  |  | 300 |  | 300 | 300 | 0 | No | 4 |  | 300 | 4.1 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Overhaul Unit (2027) - Paradise River | [5 empty] | Under $750,000 |  |  |  |  | 250 |  | 250 | 250 | 0 | No | 4 |  | 250 | 4.1 | Yes
Generation | Hydraulic Plant | Program | Roll Up |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Overhaul Hydraulic Units (2027) | [5 empty] | Under $750,000 |  |  |  |  | 550 |  | 550 | 550 | 0 | No | 4 |  | 550 | 4.1001 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Hydraulic In-Service Failures (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1640 |  | 1640 | 1640 | 0 | Yes | 4 |  | 1640 | 4.1002 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Penstock Level II Condition Assessment (2027) - Paradise River | [5 empty] | Under $750,000 |  |  |  |  | 200 |  | 200 | 200 | 0 | No | 4 |  | 200 | 4.1 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2027 |  | 2027 | Multi Year | N |  | Resurface On-Site Roads (2027-2028) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  |  |  |  | 100 | 1400 | 1500 | 1500 | 1500 | Yes | 4 |  | 100 | 4.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2027 |  | 2027 | Multi Year | N |  | Replace Powerhouse Roofs (2027-2028) - Hinds Lake | [5 empty] | Under $750,000 |  |  |  |  | 50 | 500 | 550 | 550 | 550 | No | 4 |  | 50 | 4.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Refurbish Spherical Valves Units 2 and 4 (2027-2028) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million |  |  |  |  | 200 | 550 | 750 | 750 | 550 | Yes | 4 |  | 200 | 4.2001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | West Salmon Spillway Level II Condition Assessment (2027) - Upper Salmon | [5 empty] | Under $750,000 |  |  |  |  | 400 |  | 400 | 400 | 0 | No | 4 |  | 400 | 4.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Unit 7 Major Refurbishment Turbine & Generator (2027-2029) - Bay d'Espoir | [5 empty] | Over $5 Million |  |  |  |  | 500 | 5000 | 5500 | 5500 | 5000 | Yes | 4 |  | 500 | 4.2005 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Thermal In-Service Failures (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 3607 |  | 3607 | 3607 | 0 | Yes | 4 |  | 3607 | 4.1004 | Yes
Generation | Thermal Plant | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Overhaul Unit 3 Generator and Upgrade Online Monitoring (2027) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1930.9 |  | 1930.9 | 1930.9 | 0 | Yes | 4 |  | 1930.9 | 4.1002 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Boiler Condition Assessment and Miscellaneous Upgrades (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 3500 |  | 3500 | 3500 | 0 | Yes | 4 |  | 3500 | 4.1003 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Overhaul Unit 1 Turbine Valves - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  |  | 4066.7 |  | 4066.7 | 4066.7 | 0 | Yes | 4 |  | 4066.7 | 4.1004 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Major Pump Overhaul (Unit 1 NCEP, Unit 1 EBFP, Unit 3 SCEP, Unit 3 EBFP) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1200 |  | 1200 | 1200 | 0 | Yes | 4 |  | 1200 | 4.1001 | Yes
Generation | Thermal Plant | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Fire System Upgrades (2027) | [5 empty] | Under $750,000 |  |  |  |  | 350 |  | 350 | 350 | 0 | No | 4 |  | 350 | 4.1 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Upgrade Unit 3 Synchronous Condenser Cooling Water Systems H2, Generator Lube Oil, and Seal Oil (2027) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1500 |  | 1500 | 1500 | 0 | Yes | 4 |  | 1500 | 4.1002 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Upgrade Wastewater Basin and Underground Drainage (2027) - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1000 |  | 1000 | 1000 | 0 | Yes | 4 |  | 1000 | 4.1001 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2027 | 2027 |  | Single Year | N |  | Overhaul Marine Terminal Loading Arms | [5 empty] | Under $750,000 |  |  |  |  | 550 |  | 550 | 550 | 0 | No | 4 |  | 550 | 4.1001 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2027 |  | 2027 | Multi Year | N |  | Inspect and Upgrade Light Oil System - Holyrood | [5 empty] | $1 Million to $5 Million |  |  |  |  | 200 | 800 | 1000 | 1000 | 800 | Yes | 4 |  | 200 | 4.2001 | Yes
Generation | Gas Turbines | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Gas Turbine In-Service Failures (2027) | [5 empty] | Under $750,000 |  |  |  |  | 414 |  | 414 | 414 | 0 | No | 4 |  | 414 | 4.1 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Glycol Cooler Coil (2027-2028) - Happy Valley Gas Turbine | [5 empty] | Under $750,000 |  |  |  |  | 50 | 250 | 300 | 300 | 300 | No | 4 |  | 50 | 4.2 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Fuel Pumps (2027) - Hardwoods | [5 empty] | Under $750,000 |  |  |  |  | 100 | 100 | 200 | 200 | 100 | No | 4 |  | 100 | 4.2 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Thermal Plants | [5 empty] | Under $750,000 |  |  |  |  | 50 |  | 50 | 50 | 0 | No | 4 |  | 50 | 4.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Gas Turbine | [5 empty] | Under $750,000 |  |  |  |  | 20 |  | 20 | 20 | 0 | No | 4 |  | 20 | 4.1 | Yes
Generation | Tools and Equipment | Project |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Hydraulic Plants | [5 empty] | Under $750,000 |  |  |  |  | 100 |  | 100 | 100 | 0 | No | 4 |  | 100 | 4.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Terminal Station In-Service Failures (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1579.2 |  | 1579.2 | 1579.2 | 0 | Yes | 4 |  | 1579.2 | 4.1002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Instrument Transformers (2027-2028) | [5 empty] | Under $750,000 |  |  |  |  | 360 | 240 | 600 | 600 | 240 | No | 4 |  | 360 | 4.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Protective Relays (2027-2028) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 900 | 1400 | 2300 | 2300 | 1400 | Yes | 4 |  | 900 | 4.2002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Disconnects (2027-2028) | [5 empty] | $750,000 to $1 Million |  |  |  |  | 311.5 | 578.5 | 890 | 890 | 578.5 | Yes | 4 |  | 311.5 | 4.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Upgrade Power Transformers (2027–2028) | [5 empty] | $750,000 to $1 Million |  |  |  |  | 71 | 816 | 887 | 887 | 816 | Yes | 4 |  | 71 | 4.2001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2027 |  | 2027 | Multi Year | N |  | Replace Terminal Station Battery Banks and Chargers (2027-2028) | [5 empty] | Under $750,000 |  |  |  |  | 90 | 60 | 150 | 150 | 60 | No | 4 |  | 90 | 4.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2027 | 2027 |  | Multi Year | N |  | Upgrade Terminal Station for Mobile Substation (2027-2028) - Glenburnie | [5 empty] | Under $750,000 |  |  |  |  | 60 | 400 | 460 | 460 | 460 | No | 4 |  | 60 | 4.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2027 | 2027 |  | Multi Year | N |  | Refurbish Control Building (2027-2028) | [5 empty] | Under $750,000 |  |  |  |  | 85.5 | 219.2 | 304.7 | 304.7 | 219.2 | No | 4 |  | 85.5 | 4.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Upgrade Data Alarm Systems (2027-2028) - Grand Falls Frequency Converter | [5 empty] | Under $750,000 |  |  |  |  | 60 | 90 | 150 | 150 | 90 | No | 4 |  | 60 | 4.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2027 | 2027 |  | Multi Year | N |  | Upgrade Transformer Paralleling (2027-2028) - Bottom Brook | [5 empty] | Under $750,000 |  |  |  |  | 36 | 54 | 90 | 90 | 54 | No | 4 |  | 36 | 4.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Circuit Breaker Reclosing Controllers (2027-2028) - Roddickton | [5 empty] | Under $750,000 |  |  |  |  | 54 | 71 | 125 | 125 | 71 | No | 4 |  | 54 | 4.2 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | General Plant | 2027 | 2027 |  | Single Year | N |  | Upgrade Drainage to Stop Frost Heaving (2027) - Stoney Brook, Springdale, Holyrood, Jackson's Arm, and Buchans | [5 empty] | Under $750,000 |  |  |  |  | 250 |  | 250 | 250 | 0 | No | 4 |  | 250 | 4.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Transformer T3 (2027-2028) - Bay d'Espoir | [5 empty] | $1 Million to $5 Million |  |  |  |  | 900 | 1900 | 2800 | 2800 | 1900 | Yes | 4 |  | 900 | 4.2003 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Replace Transformer T3 (2027-2028) - Wabush Terminal Station | [5 empty] | Over $5 Million |  |  |  |  | 1254 | 4959 | 6213 | 6213 |  | Yes | 4 |  | 1254 | 4.2006 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Install Breaker Failure Protection (2027-2028) - Western Avalon | [5 empty] | Under $750,000 |  |  |  |  | 135 | 315 | 450 | 450 | 315 | No | 4 |  | 135 | 4.2 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Transmission In-Service Failures (2027) | [5 empty] | Under $750,000 |  |  |  |  | 170 |  | 170 | 170 | 0 | No | 4 |  | 170 | 4.1 | Yes
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Wood Pole Line Management (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 4767 |  | 4767 | 4767 | 0 | Yes | 4 |  | 4767 | 4.1005 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Access | 2027 |  | 2027 | Single Year | N |  | Provide Service Extensions (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 4567 |  | 4567 | 4567 | 0 | Yes | 4 |  | 4567 | 4.1005 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Distribution System In-Service Failures, Miscellaneous Upgrades, and Street Lights (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 4167 |  | 4167 | 4167 | 0 | Yes | 4 |  | 4167 | 4.1004 | Yes |  |  |  | MOVED from 2023 to 2026 in 2022 CBA prep
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2027 | 2027 |  | Multi Year | N |  | Upgrade Worst-Performing Distribution Feeders (2027-2028) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 480.26 | 2719.95 | 3200.21 | 3200.21 | 2719.95 | Yes | 4 |  | 480.26 | 4.2003 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2027 | 2027 |  | Multi Year | N |  | Renew Distribution Feeders (2027-2028) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1287.3 | 1245.1 | 2532.4 | 2532.4 | 1245.1 | Yes | 4 |  | 1287.3 | 4.2003 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2027 | 2027 |  | Multi Year | N |  | Distribution Equipment SCADA Additions (2027-2028) | [5 empty] | Under $750,000 |  |  |  |  | 30 | 270 | 300 | 300 | 270 | No | 4 |  | 30 | 4.2 | Yes
Transmission and Rural Operations | Distribution | Project |  |  | System Growth | 2027 |  | 2027 | Single Year | N |  | Additions for Load (2027) - Distribution System | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1000 |  | 1000 | 1000 | 0 | Yes | 4 |  | 1000 | 4.1001 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Overhaul Diesel Units (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1500 |  | 1500 | 1500 | 0 | Yes | 4 |  | 1500 | 4.1002 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Diesel In-Service Failures (2027) | [5 empty] | Under $750,000 |  |  |  |  | 495 |  | 495 | 495 | 0 | No | 4 |  | 495 | 4.1 | Yes
Transmission and Rural Operations | Generation | Project |  |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Inspect Fuel Storage Tanks (2027) - Hawke's Bay | [5 empty] | Under $750,000 |  |  |  |  | 300 |  | 300 | 300 | 0 | No | 4 |  | 300 | 4.1 | Yes
Transmission and Rural Operations | Generation | Project |  |  | System Growth | 2027 |  | 2027 | Single Year | N |  | Additions for Load Growth - Isolated Generation Stations (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1500 |  | 1500 | 1500 | 0 | Yes | 4 |  | 1500 | 4.1002 | Yes
Transmission and Rural Operations | Generation | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Replace Roof (2027) - Cartwright | [5 empty] | Under $750,000 |  |  |  |  | 700 |  | 700 | 700 | 0 | No | 4 |  | 700 | 4.1001 | Yes
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Upgrade Outside Property (2027) - St. Anthony, Bishop's Falls, Stephenville, and Whitbourne | [5 empty] | Under $750,000 |  |  |  |  | 428 |  | 428 | 428 | 0 | No | 4 |  | 428 | 4.1 | Yes
Transmission and Rural Operations | Metering | Program | Standalone |  | Access | 2027 |  | 2027 | Single Year | N |  | Purchase Meters and Metering Equipment (2027) | [5 empty] | Under $750,000 |  |  |  |  | 629.5 |  | 629.5 | 629.5 | 0 | No | 4 |  | 629.5 | 4.1001 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Central Region | [5 empty] | Under $750,000 |  |  |  |  | 180 |  | 180 | 180 | 0 | No | 4 |  | 180 | 4.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Northern Region | [5 empty] | Under $750,000 |  |  |  |  | 120 |  | 120 | 120 | 0 | No | 4 |  | 120 | 4.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Labrador Region | [5 empty] | Under $750,000 |  |  |  |  | 100 |  | 100 | 100 | 0 | No | 4 |  | 100 | 4.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | 2027 | 2027 |  | Multi Year | N |  | Replace Off Road Heavy-Duty Equipment (2027-2028) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 500 | 500 | 1000 | 1000 | 500 | Yes | 4 |  | 500 | 4.2001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Upgrade Software Applications (2027) | [5 empty] | Under $750,000 |  |  |  |  | 100 |  | 100 | 100 | 0 | No | 4 |  | 100 | 4.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Perform Software Upgrades and Minor Enhancements (2027) | [5 empty] | Under $750,000 |  |  |  |  | 625 |  | 625 | 625 | 0 | No | 4 |  | 625 | 4.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Update Cyber Security Infrastructure (2027) | [5 empty] | Under $750,000 |  |  |  |  | 350 |  | 350 | 350 | 0 | No | 4 |  | 350 | 4.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Personal Computers (2027) | [5 empty] | $750,000 to $1 Million |  |  |  |  | 986.6 |  | 986.6 | 986.6 | 0 | Yes | 4 |  | 986.6 | 4.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Replace Peripheral Infrastructure (2027) | [5 empty] | Under $750,000 |  |  |  |  | 269.1 |  | 269.1 | 269.1 | 0 | No | 4 |  | 269.1 | 4.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Upgrade Core OT Infrastructure (2027) | [5 empty] | Under $750,000 |  |  |  |  | 375 |  | 375 | 375 | 0 | No | 4 |  | 375 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Minor Telecommunications Enhancements (2027) | [5 empty] | Under $750,000 |  |  |  |  | 104.8 |  | 104.8 | 104.8 | 0 | No | 4 |  | 104.8 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Mobile Devices (2027) | [5 empty] | Under $750,000 |  |  |  |  | 183.4 |  | 183.4 | 183.4 | 0 | No | 4 |  | 183.4 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Upgrade Remote Terminal Units (2027) | [5 empty] | Under $750,000 |  |  |  |  | 179 |  | 179 | 179 | 0 | No | 4 |  | 179 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Site Physical Security Program (2027) | [5 empty] | Under $750,000 |  |  |  |  | 116 |  | 116 | 116 | 0 | No | 4 |  | 116 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Replace Network Communications Equipment (2027) | [5 empty] | Under $750,000 |  |  |  |  | 229 |  | 229 | 229 | 0 | No | 4 |  | 229 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2027) - Telecontrol | [5 empty] | Under $750,000 |  |  |  |  | 49.7 |  | 49.7 | 49.7 | 0 | No | 4 |  | 49.7 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Replace 48 V Battery Banks and Chargers (2027) | [5 empty] | Under $750,000 |  |  |  |  | 454.4 |  | 454.4 | 454.4 | 0 | No | 4 |  | 454.4 | 4.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2027 |  | 2027 | Single Year | N |  | Telecommunications Tower Condition Management (2027) | [5 empty] | Under $750,000 |  |  |  |  | 99 |  | 99 | 99 | 0 | No | 4 |  | 99 | 4.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2027 |  | 2027 | Multi Year | N |  | Replace Power Line Carrier (2027-2028) - TL212 | [5 empty] | $750,000 to $1 Million |  |  |  |  | 93.6 | 681.4 | 775 | 775 | 681.4 | Yes | 4 |  | 93.6 | 4.2001 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Telecommunications In-Service Failure (2027) | [5 empty] | Under $750,000 |  |  |  |  | 99 |  | 99 | 99 | 99 | No | 4 |  | 99 | 4.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Install CCTV Systems (2027) | [5 empty] | Under $750,000 |  |  |  |  | 212.2 |  | 212.2 | 212.2 | 212.2 | No | 4 |  | 212.2 | 4.1 | Yes
General Properties | Telecontrol | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Replace Cisco Call Manager Appliances | [5 empty] | Under $750,000 |  |  |  |  | 130 |  | 130 | 130 | 130 | No | 4 |  | 130 | 4.1 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2027 | 2027 |  | Multi Year | N |  | Replace Light- and Heavy-Duty Vehicles (2027-2028) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 2000 | 2000 | 4000 | 4000 | 2000 | Yes | 4 |  | 2000 | 4.2004 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Replace Mobile Equipment (2027) | [5 empty] | Under $750,000 |  |  |  |  | 600 |  | 600 | 600 | 0 | No | 4 |  | 600 | 4.1001 | Yes
General Properties | Administration | Program | Standalone |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Purchase Furniture & Equipment Less Than $50,000 (2027) | [5 empty] | Under $750,000 |  |  |  |  | 68 |  | 68 | 68 | 0 | No | 4 |  | 68 | 4.1 | Yes
General Properties | Administration | Program | Standalone |  | Service Enhancement | 2027 |  | 2027 | Single Year | N |  | Remove Safety Hazards (2027) | [5 empty] | Under $750,000 |  |  |  |  | 218 |  | 218 | 218 | 0 | No | 4 |  | 218 | 4.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2027 |  | 2027 | Single Year | N |  | Fire Panel and Device Upgrade (2027) | [5 empty] | Under $750,000 |  |  |  |  | 197 |  | 197 | 197 |  | No | 4 |  | 197 | 4.1 | Yes
Allowance for Unforeseen Items |  | Program | Standalone |  | Allowance for Unforeseen | 2027 |  | 2027 | Single Year | N |  | Allowance for Unforeseen Items (2027) | [5 empty] | $1 Million to $5 Million |  |  |  |  | 1000 |  | 1000 | 1000 | 0 | Yes | 4 |  | 1000 | 4.1001 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Overhaul Unit 4 (2028) - Bay d'Espoir | [5 empty] | Under $750,000 | [5 empty] | 300 | 300 | 300 |  | No | 3 |  | 300 | 3.1 | Yes
Generation | Hydraulic Plant | Program | Hydraulic Unit Overhauls Program |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Overhaul Unit 6 (2028) - Bay d'Espoir | [5 empty] | Under $750,000 | [5 empty] | 300 | 300 | 300 |  | No | 3 |  | 300 | 3.1 | Yes
Generation | Hydraulic Plant | Program | Roll Up |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Overhaul Hydraulic Units (2028) | [5 empty] | Under $750,000 | [5 empty] | 600 | 600 | 600 |  | No | 3 |  | 600 | 3.1001 | Yes
Generation | Hydraulic Plant | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Hydraulic In Service Failures (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 1677 | 1677 | 1677 |  | Yes | 3 |  | 1677 | 3.1002 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2028 | 2028 |  | Single Year | N |  | Rehabilitate Access Roads - Powerhouse, Intake, and North Salmon Spillway (2028-2029) - Upper Salmon | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2028 | 2028 |  | Single Year | N |  | Refurbish Blue Grass Access Road - Spillway to Dam (2028-2029) - Hinds Lake | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes |  |  |  | changed POV to Port Saunders
Generation | Hydraulic Plant | Project |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Refurbish CD4 Rip Rap (2028) - Cat Arm | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Replace Powerhouse 2 Roof (2028) - Bay d'Espoir | [5 empty] | $750,000 to $1 Million | [5 empty] | 960 | 960 | 960 |  | Yes | 3 |  | 960 | 3.1001 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Replace Station Service (2028) - Hind's Lake | [5 empty] | $750,000 to $1 Million | [5 empty] | 900 | 900 | 900 |  | Yes | 3 |  | 900 | 3.1001 | Yes
Generation | Hydraulic Plant | Project |  |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Refurbish Rip Rap Material on SD-1 (2028) - North Salmon Dam | [5 empty] | Under $750,000 | [5 empty] | 450 | 450 | 450 |  | No | 3 |  | 450 | 3.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Refurbish Spherical Valves Unit 3 (2028-2029) - Bay d'Espoir | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
Generation | Hydraulic Plant | Project |  |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Major Refurbishment Turbine & Generator (2028-2029) - Upper Salmon | [5 empty] | Under $750,000 | [5 empty] | 500 | 500 | 500 |  | No | 3 |  | 500 | 3.1 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Thermal In-Service Failures (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 3686 | 3686 | 3686 |  | Yes | 3 |  | 3686 | 3.1004 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Overhaul Unit 3 Turbine Valves | [5 empty] | $1 Million to $5 Million | [5 empty] | 4270 | 4270 | 4270 |  | Yes | 3 |  | 4270 | 3.1004 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Boiler Condition Assessment and Miscellaneous Upgrades (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 3500 | 3500 | 3500 |  | Yes | 3 |  | 3500 | 3.1004 | Yes
Generation | Thermal Plant | Program |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Major Pump Overhaul (Unit 2 NCEP, Unit 2 ECWP ) | [5 empty] | Under $750,000 | [5 empty] | 450 | 450 | 450 |  | No | 3 |  | 450 | 3.1 | Yes
Generation | Thermal Plant | Project |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Condition Assessment of doors siding and roofing | [5 empty] | Under $750,000 | [5 empty] | 120 | 120 | 120 |  | No | 3 |  | 120 | 3.1 | Yes
Generation | Gas Turbines | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Gas Turbine In-Service Failures (2028) | [5 empty] | Under $750,000 | [5 empty] | 435 | 435 | 435 |  | No | 3 |  | 435 | 3.1 | Yes
Generation | Gas Turbines | Project |  |  | Service Enhancement | 2028 | 2028 |  | Single Year | N |  | Upgrade Rotor (2028-2029) - Holyrood Gas Turbine | [5 empty] | $1 Million to $5 Million | [5 empty] | 2000 | 2000 | 2000 | 2000 | Yes | 3 |  | 2000 | 3.1002 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Major Inspection (2028) - Holyrood Gas Turbine | [5 empty] | Over $5 Million | [5 empty] | 7500 |  | 7500 |  | Yes | 3 |  | 7500 | 3.1008 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Thermal Plants | [5 empty] | Under $750,000 | [5 empty] | 50 | 50 | 50 |  | No | 3 |  | 50 | 3.1 | Yes
Generation | Tools and Equipment | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Gas Turbine | [5 empty] | Under $750,000 | [5 empty] | 20 | 20 | 20 |  | No | 3 |  | 20 | 3.1 | Yes
Generation | Tools and Equipment | Project |  |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Hydraulic Plants | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Terminal Station In-service Failures (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 1685 | 1685 | 1685 |  | Yes | 3 |  | 1685 | 3.1002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Replace Instrument Transformers (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 250 | 250 | 250 |  | No | 3 |  | 250 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Replace Protective Relays (2028-2029) | [5 empty] | $750,000 to $1 Million | [5 empty] | 800 | 800 | 800 |  | Yes | 3 |  | 800 | 3.1001 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Replace Disconnects (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 370 | 370 | 370 |  | No | 3 |  | 370 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Upgrade Power Transformers (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 90 | 90 | 90 |  | No | 3 |  | 90 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Renew Circuit Breakers (2028-2029) | [5 empty] | $1 Million to $5 Million | [5 empty] | 2100 | 2100 | 2100 |  | Yes | 3 |  | 2100 | 3.1002 | Yes
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Replace Terminal Station Battery Banks and Chargers (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 150 | 150 | 150 |  | No | 3 |  | 150 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2028 | 2028 |  | Single Year | N |  | Upgrade Terminal Station for Mobile Substation (2028-2029) - Roddickton | [5 empty] | Under $750,000 | [5 empty] | 60 | 60 | 60 | 60 | No | 3 |  | 60 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | 2028 | 2028 |  | Single Year | N |  | Upgrade Transformer Paralleling (2028-2029) - Bay d'Espoir Terminal Station 2 | [5 empty] | Under $750,000 | [5 empty] | 36 | 36 | 36 |  | No | 3 |  | 36 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Replace Equipment Foundations (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 280 | 280 | 280 |  | No | 3 |  | 280 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Upgrade Data Alarm Systems (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Upgrade Reclosing Circuit Breakers (2028-2029) - Berry Hill | [5 empty] | Under $750,000 | [5 empty] | 54 | 54 | 54 |  | No | 3 |  | 54 | 3.1 | Yes
Transmission and Rural Operations | Terminal Stations | Project |  |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Upgrade Drainage to Stop Frost Heaving (2028) - Stoney Brook, Springdale, Holyrood, Jackson's Arm, Buchan's Terminal Stations | [5 empty] | Under $750,000 | [5 empty] | 250 | 250 | 250 |  | No | 3 |  | 250 | 3.1 | Yes |  |  |  | MOVED from 2025 to 2026 in 2022 CBA prep, then to 2027 in 2023 CBA prep
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Transmission In-Service Failures (2028) | [5 empty] | Under $750,000 | [5 empty] | 174 | 174 | 174 |  | No | 3 |  | 174 | 3.1 | Yes |  |  | was 415 in 2027 | DEFERRED from 2023 to 2027 in 2023 CBA prep then cancelled
Transmission and Rural Operations | Transmission | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Wood Pole Line Management (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 2474 | 2474 | 2474 |  | Yes | 3 |  | 2474 | 3.1002 | Yes |  |  |  | MOVED from 2026 to 2027 in 2022 CBA prep
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2028 | 2028 |  | Single Year | N |  | Upgrade Worst-Performing Distribution Feeders (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 480.26 | 480.26 | 480.26 |  | No | 3 |  | 480.26 | 3.1 | Yes |  |  |  | cancelled in 2023 CBA Prep
Transmission and Rural Operations | Distribution | Program | Standalone |  | Access | 2028 | 2028 |  | Single Year | N |  | Provide Service Extensions (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 4670 | 4670 | 4670 |  | Yes | 3 |  | 4670 | 3.1005 | Yes |  |  | was 200 in 2027 | cancelled in 2023 CBA Prep
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Distribution System In-Service Failures, Miscellaneous Upgrades and Street Lights (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 4284 | 4284 | 4284 |  | Yes | 3 |  | 4284 | 3.1004 | Yes |  |  | was 400 in 2027 | cancelled in 2023 CBA Prep
Transmission and Rural Operations | Distribution | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Renew Distribution Feeders (2028-2029) | [5 empty] | $1 Million to $5 Million | [5 empty] | 1287.3 | 1287.3 | 1287.3 |  | Yes | 3 |  | 1287.3 | 3.1001 | Yes
Transmission and Rural Operations | Distribution | Program | Standalone |  | Service Enhancement | 2028 | 2028 |  | Single Year | N |  | Distribution Equipment SCADA Additions (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 30 | 30 | 30 |  | No | 3 |  | 30 | 3.1 | Yes
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Diesel Genset Replacement (2028) - Makkovik | [5 empty] | Under $750,000 | [5 empty] | 500 | 500 | 500 |  | No | 3 |  | 500 | 3.1 | Yes
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Diesel Genset Replacement (2028) - Cartwright | [5 empty] | Under $750,000 | [5 empty] | 500 | 500 | 500 |  | No | 3 |  | 500 | 3.1 | Yes
Transmission and Rural Operations | Generation | Program | Roll Up |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Replace Diesel Gensets (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 1000 | 1000 | 1000 |  | Yes | 3 |  | 1000 | 3.1001 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2028 | 2028 |  | Single Year | N |  | Overhaul Diesel Units (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 2250 | 2250 | 2250 |  | Yes | 3 |  | 2250 | 3.1002 | Yes
Transmission and Rural Operations | Generation | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Diesel In-Service Failures (2028) | [5 empty] | Under $750,000 | [5 empty] | 500 | 500 | 500 |  | No | 3 |  | 500 | 3.1 | Yes |  |  | was 321.9 in 2027 | DEFERRED FROM 2021 to 2027, then cancelled in 2023 CBA prep
Transmission and Rural Operations | Generation | Project |  |  | System Growth | 2028 | 2028 |  | Single Year | N |  | Additions for Load Growth - Isolated Generation Stations (2028) | [5 empty] | Under $750,000 | [5 empty] | 650 | 650 | 650 |  | No | 3 |  | 650 | 3.1001 | Yes |  |  | was 250 in 2027
Transmission and Rural Operations | Properties | Project |  |  | General Plant | 2028 | 2028 |  | Single Year | N |  | Upgrade Property (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 1150 | 1150 | 1150 |  | Yes | 3 |  | 1150 | 3.1001 | Yes |  |  | was 125 in 2027 | MOVED from 2023 to 2027
Transmission and Rural Operations | Metering | Program | Standalone |  | Access | 2028 |  | 2028 | Single Year | N |  | Purchase Meters and Metering Equipment (2028) | [5 empty] | Under $750,000 | [5 empty] | 395.5 | 395.5 | 395.5 |  | No | 3 |  | 395.5 | 3.1 | Yes |  |  | was 1600 in 2027
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Central Region | [5 empty] | Under $750,000 | [5 empty] | 180 | 180 | 180 |  | No | 3 |  | 180 | 3.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Northern Region | [5 empty] | Under $750,000 | [5 empty] | 120 | 120 | 120 |  | No | 3 |  | 120 | 3.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Labrador Region | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | 2028 | 2028 |  | Single Year | N |  | Replace Off Road Heavy-Duty Equipment (2028-2029) | [5 empty] | Under $750,000 | [5 empty] | 500 | 500 | 500 |  | No | 3 |  | 500 | 3.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Upgrade Energy Management System (2028) | [5 empty] | Under $750,000 | [5 empty] | 380 | 380 | 380 |  | No | 3 |  | 380 | 3.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Perform Software Upgrades and Minor Enhancements (2028) | [5 empty] | Under $750,000 | [5 empty] | 725 | 725 | 725 |  | No | 3 |  | 725 | 3.1001 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Update Cyber Security Infrastructure (2028) | [5 empty] | Under $750,000 | [5 empty] | 375 | 375 | 375 |  | No | 3 |  | 375 | 3.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Personal Computers (2028) | [5 empty] | Under $750,000 | [5 empty] | 325.8 | 325.8 | 325.8 |  | No | 3 |  | 325.8 | 3.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Replace Peripheral Infrastructure (2028) | [5 empty] | Under $750,000 | [5 empty] | 105.9 | 105.9 | 105.9 |  | No | 3 |  | 105.9 | 3.1 | Yes
General Properties | Information Systems | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Upgrade Core OT Infrastructure (2028) | [5 empty] | Under $750,000 | [5 empty] | 425 | 425 | 425 |  | No | 3 |  | 425 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Telecommunications In-Service Failure (2028) | [5 empty] | Under $750,000 | [5 empty] | 102 | 102 | 102 |  | No | 3 |  | 102 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Purchase Mobile Devices (2028) | [5 empty] | Under $750,000 | [5 empty] | 144 | 144 | 144 |  | No | 3 |  | 144 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Install CCTV Cameras (2028) | [5 empty] | Under $750,000 | [5 empty] | 218.5 | 218.5 | 218.5 |  | No | 3 |  | 218.5 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Tools and Equipment Less than $50,000 (2028) - Telecontrol | [5 empty] | Under $750,000 | [5 empty] | 49.7 | 49.7 | 49.7 |  | No | 3 |  | 49.7 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Replace 48 V Battery Banks and Chargers (2028) | [5 empty] | Under $750,000 | [5 empty] | 468 | 468 | 468 |  | No | 3 |  | 468 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Replace Network Communications Equipment (2028) | [5 empty] | Under $750,000 | [5 empty] | 236 | 236 | 236 |  | No | 3 |  | 236 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Minor Telecommunications Enhancement (2028) | [5 empty] | Under $750,000 | [5 empty] | 107.9 | 107.9 | 107.9 |  | No | 3 |  | 107.9 | 3.1 | Yes
General Properties | Telecontrol | Program | Standalone |  | Renewal | 2028 |  | 2028 | Single Year | N |  | Upgrade Remote Terminal Units (2028) | [5 empty] | Under $750,000 | [5 empty] | 184 | 184 | 184 |  | No | 3 |  | 184 | 3.1 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2028 | 2028 |  | Single Year | N |  | Replace Light- and Heavy-Duty Vehicles (2028-2029) | [5 empty] | $1 Million to $5 Million | [5 empty] | 2000 | 2000 | 2000 |  | Yes | 3 |  | 2000 | 3.1002 | Yes
General Properties | Transportation | Program | Standalone |  | General Plant | 2028 | 2028 |  | Single Year | N |  | Replace Mobile Equipment (2028) | [5 empty] | Under $750,000 | [5 empty] | 600 | 600 | 600 |  | No | 3 |  | 600 | 3.1001 | Yes
General Properties | Administration | Program | Standalone |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Purchase Furniture & Equipment Less Than $50,000 (2028) | [5 empty] | Under $750,000 | [5 empty] | 68 | 68 | 68 |  | No | 3 |  | 68 | 3.1 | Yes
General Properties | Administration | Program | Standalone |  | Service Enhancement | 2028 |  | 2028 | Single Year | N |  | Remove Safety Hazards (2028) | [5 empty] | Under $750,000 | [5 empty] | 200 | 200 | 200 |  | No | 3 |  | 200 | 3.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Replace Fuel Tank, Lines, Pumps and Associated Hardware | [5 empty] | Under $750,000 | [5 empty] | 100 | 100 | 100 |  | No | 3 |  | 100 | 3.1 | Yes
General Properties | Administration | Project |  |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Replace Generators and Associated Switchgear | [5 empty] | $1 Million to $5 Million | [5 empty] | 1000 | 1000 | 1000 |  | Yes | 3 |  | 1000 | 3.1001 | Yes
General Properties | Administration | Project |  |  | General Plant | 2028 |  | 2028 | Single Year | N |  | Replace Multi-Stack Chiller Level 1 Mechanical Room | [5 empty] | Under $750,000 | [5 empty] | 200 | 200 | 200 |  | No | 3 |  | 200 | 3.1 | Yes
Allowance for Unforeseen Items |  | Program | Standalone |  | Allowance for Unforeseen | 2028 |  | 2028 | Single Year | N |  | Allowance for Unforeseen Items (2028) | [5 empty] | $1 Million to $5 Million | [5 empty] | 1000 | 1000 | 1000 |  | Yes | 3 |  | 1000 | 3.1001 | Yes
Generation | Gas Turbines | Project |  |  | Renewal | 2029 |  | 2029 | Single Year | N |  | Replace FOWI pumps - Holyrood Gas Turbine | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 |  | No | 2 |  | 0 | 2 | No
Generation | Gas Turbines | Project |  |  | Renewal | 2029 | 2029 |  | Single Year | N |  | Install Water Wash Skid - Holyrood Gas Turbine | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 |  | No | 2 |  | 0 | 2 | No
Generation | Hydraulic Plant | Program | Standalone |  | Service Enhancement | CANCELLED |  |  | Single Year |  |  | Upgrade Public Safety Around Dams and Waterways (2024) | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year | N |  | Install Automated Fuel Monitoring System West Salmon Spillway (2025) - Upper Salmon | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year | N |  | Install Automated Fuel Monitoring System North salmon Spillway (2025) - Upper Salmon | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year | N |  | Install Remote Crane Pendant (2025) - Upper Salmon | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Replace Underground Oily Water Separator (2025) - Bay d'Espoir | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Steel Liner and Bifurcation Condition Assessment (2025) - Cat Arm | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Replace Guide Bearing Segments and Install High-Pressure Lift System Units 1 to 6 (2026-2027) - Bay d'Espoir | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Refurbish Mechanical Governors (2027–2028) - Bay d'Espoir | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year |  |  | Replace Station Service Transformer 2 (2024-2025) - Bay d'Espoir | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Hydraulic Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year |  |  | Replace Station Cooling Water Piping, Valves, and Controls (2024) - Upper Salmon | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Thermal Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Overhaul Fuel Oil Storage Tank #3 | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Thermal Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Upgrade Generator Protection Unit 1 and Unit 2 | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Thermal Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year |  |  | Apply Protective Coating on Concrete Stacks | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Thermal Plant | Project |  |  | Renewal | CANCELLED |  |  | Single Year |  |  | Upgrade Turbine Supervisory Instrumentation - Holyrood (cancel) | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Generation | Thermal Plant | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year |  |  | Upgrade Ambient Monitoring Stations (2024-2025) - Holyrood | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Transmission and Rural Operations | Terminal Stations | Program | Standalone |  | Renewal | CANCELLED | 2027 |  | Single Year | N |  | Renew Circuit Breakers (2027-2028) | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Transmission and Rural Operations | Terminal Stations | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year | N |  | Upgrade Transformer Paralleling (2024-2025) - Holyrood T5 & T10 | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2025 |  | Single Year | N |  | Upgrade Work (2026-2031) - L23 and L24 | [5 empty] | Under $750,000 | [6 empty] | 0 | 0 | 0 | No | 0 |  | 0 | 0 | No
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2026 |  | Single Year | N |  | Upgrade Work (2027-2028) - TL202 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2026 |  | Single Year | N |  | Upgrade Work (2027-2030) - TL204 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2026 |  | Single Year | N |  | Upgrade Work (2027-2031) - TL212 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2027 |  | Single Year | N |  | Upgrade Work (2028-2031) - TL205 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2027 |  | Single Year | N |  | Upgrade Work (2028-2031) - TL211 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2027 |  | Single Year | N |  | Upgrade Work (2028-2032) - TL214 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2027 |  | Single Year | N |  | Upgrade Work (2027-2031) - TL228 | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2028 |  | Single Year | N |  | Upgrade Work (2029-2033) - TL206 | [12 empty] | 0 | 0 | [5 empty] | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED | 2028 |  | Single Year | N |  | Upgrade Work (2029-2030) - TL208 | [12 empty] | 0 | 0 | [5 empty] | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED |  |  | Single Year |  |  | Upgrade Work | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Transmission | Project |  |  | Renewal | CANCELLED |  |  | Single Year |  |  | Upgrade Work | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Distribution | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year | N |  | Install Recloser Remote Control (2025-2026) - Various | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Distribution | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year | N |  | Implement Geographical Information System (2025-2026) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Distribution | Project |  |  | Service Enhancement | CANCELLED |  |  | Single Year |  |  | Install Recloser Remote Control (2024-2025) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Distribution |  |  |  |  | CANCELLED |  |  | Single Year |  |  | Replace Poles and Replace #4 Copper Wire Primary | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | CANCELLED |  | 2026 | Single Year | N |  | Replace Diesel Genset (2026) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Generation | Program | Diesel Genset Replacement Program |  | Renewal | CANCELLED |  | 2027 | Single Year | N |  | Replace Diesel Genset (2027) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Generation | Program | Roll Up |  | Renewal | CANCELLED |  | 2026 | Single Year | N |  | Replace Diesel Gensets (2026) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Generation | Program | Roll Up |  | Renewal | CANCELLED |  | 2027 | Single Year | N |  | Replace Diesel Gensets (2027) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Generation | Project |  |  | Renewal | CANCELLED |  |  | Single Year | N |  | Replace Diesel Plant (2025-2026) - Paradise River | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Generation | Project |  |  | System Growth | CANCELLED |  | 2024 | Single Year | N |  | Additions for Load Growth - Isolated Generation Stations (2024) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Properties | Project |  |  | General Plant | CANCELLED |  |  | Single Year | N |  | Upgrade Line Depots (2026-2027) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Properties | Project |  |  | General Plant | CANCELLED |  |  | Single Year | N |  | Upgrade Line Depots (2027-2028) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Transmission and Rural Operations | Tools and Equipment | Project |  |  | General Plant | CANCELLED |  |  | Single Year |  |  | Replace Back Hoe Unit 9813 (2024) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
General Properties | Properties | Project |  |  | General Plant | CANCELLED |  |  | Single Year |  |  | Purchase and Install Accomodations Trailer - Postville | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
General Properties | Administration | Project |  |  | Renewal | CANCELLED |  | 2027 | Single Year | N |  | Replace/Upgrade Motor Control Centre Building Power Service (2027) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
General Properties | Administration | Project |  |  | General Plant | CANCELLED |  | 2025 | Single Year | N |  | Upgrade Septic System (2025) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
General Properties | Administration | Project |  |  | General Plant | CANCELLED |  |  | Single Year |  |  | Replace Parking Lot Lighting and Fixtures (2024) - Hydro Place | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Hydraulic Plant | Project |  |  | General Plant | DEFERRED |  |  | Single Year | N |  | Resurface Access Road from St. Albans to Upper Salmon and West Salmon Spillway (2027) - Upper Salmon | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Hydraulic Plant | Project |  |  | Renewal | DEFERRED | 2028 |  | Single Year | N |  | Replace Low Pressure Compressor, Piping and Controls - HLK | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Hydraulic Plant | Project |  |  | Renewal | DEFERRED | 2028 |  | Single Year | N |  | Refurbish Mechanical Governors - BDE | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Hydraulic Plant | Project |  |  | Renewal | DEFERRED | 2028 |  | Single Year | N |  | Penstock Refurbishment - BDE3 - new Sept 2 | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Hydraulic Plant | Project |  |  | Renewal | DEFERRED | 2028 |  | Single Year | N |  | Refurbish Spillway (2028-2029) - North Salmon | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Hydraulic Plant | Project |  |  | General Plant | DEFERRED |  | 2028 | Single Year | N |  | PRV-Replace Accomodation Facility | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Hydraulic Plant | Project |  |  | General Plant | DEFERRED |  | 2028 | Single Year | N |  | BDE - Road Refurbishment from Granite to Burnt Dam | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Hydraulic Plant | Project |  |  | Renewal | DEFERRED |  | 2028 | Single Year | N |  | Refurbish Mechanical Governors (2027) - BDE - (From 2025) | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Thermal Plant | Project |  |  | General Plant | DEFERRED | 2025 |  | Single Year | N |  | Install Plant Heating (2024-2025) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | General Plant | DEFERRED | 2025 |  | Single Year | N |  | Install Plant Heating Interim Solution | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED | 2025 |  | Single Year | N |  | Replace Electrical Distribution System (2025-2027) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | General Plant | DEFERRED |  | 2025 | Single Year | N |  | Upgrade Water Treatment Plant and Waste Water Treatment Plant (2025) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED |  | 2025 | Single Year | N |  | Upgrade Black Start Diesel Cables (2025) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED | 2025 |  | Single Year | N |  | Inspect and Upgrade Light Oil System - Holyrood (2025-2026) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | General Plant | DEFERRED |  | 2025 | Single Year | N |  | Upgrade Control Room Fire Rating (2025) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | General Plant | DEFERRED | 2025 |  | Single Year | N |  | Install Energy Efficient High Bay and Exterior Lighting (2025-2026) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED | 2025 |  | Single Year | N |  | Upgrade Unit 3 Breeching - Re-insulate Exterior | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Service Enhancement | DEFERRED |  | 2025 | Single Year | N |  | Upgrade Vibration Monitoring Equipment Unit 3 Generator (2025) | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED | 2025 |  | Single Year | N |  | Upgrade DCS - Unit 1, Unit 2, Unit 3 Boiler (2025-2026) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED | 2027 |  | Single Year | N |  | Install New Oil Systems Unit 3 (2027-2028) - Holyrood | [12 empty] | 0 | 0 | 0 |  |  |  |  | 0
Generation | Thermal Plant | Project |  |  | Renewal | DEFERRED |  | 2028 | Single Year | N |  | Revisit Condition Assessment - Level 1 | [12 empty] | 0 | 0 | [5 empty] | 0
Generation | Thermal Plant | Project |  |  | General Plant | DEFERRED |  | 2028 | Single Year | N |  | Upgrade Powerhouse Doors, Siding and Roofing | [13 empty] | 0 | [5 empty] | 0
Transmission and Rural Operations | Properties | Project |  |  | General Plant | DEFERRED |  |  | Single Year |  |  | Upgrade Property (2024) - St. Anthony (added to another project) | [13 empty] | 0 | [5 empty] | 0
General Properties | Administration | Project |  |  | General Plant | DEFERRED |  | 2027 | Single Year | N |  | Replace Security Gate Controls (2027) | [13 empty] | 0 | [5 empty] | 0
General Properties | Administration | Project |  |  | General Plant | DEFERRED |  | 2028 | Single Year | N |  | Replace Emergency Power Transfer Switch System | [13 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0 | [5 empty] | 0
[9 empty] | Single Year | [16 empty] | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[9 empty] | Single Year | [15 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
[25 empty] | 0 | 0 | 0
Note on M90: Justin Haley: Dummy Line for Purchase Spare GSU as required for Revision 1
Note on AB3: Roger Pope: Formula

## Sched A - 2024 M.A Under 750k
Newfoundland and Labrador Hydro
2024 Capital Budget Application
Detailed Breakdown By Minor Asset Category for 2024 Expenditures (Under $750,000)
($000)
Commencement Year | 2024
Range | - multiple -
Supplemental Y/N | - multiple -
Program Subcategory | - multiple -
SY-Start Year | - multiple -
Main Cat | Sub Cat | CBA Description | 2024
Generation
Gas Turbines
|  | Gas Turbine In-Service Failures (2024) | 358
|  | Inspect Fuel Tanks (2024) - Hardwoods Gas Turbines | 692.9
| Gas Turbines Result |  | 1050.9
Hydraulic Plant
|  | Penstock Level II Condition Assessment (2024) - Upper Salmon | 382.8
|  | Overhaul Hydraulic Units (2024) | 323.8
|  | Replace Timber Crib and Insulation (2024) - Burnt Dam Spillway | 161.8
|  | Install Anemometer (2024) - Cat Arm | 68.6
| Hydraulic Plant Result |  | 937
Thermal Plant
|  | Overhaul Pumps (2024) - Holyrood | 661
|  | Overhaul Marine Terminal Loading Arms (2024) - Holyrood | 511
| Thermal Plant Result |  | 1172
Tools and Equipment
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Gas Turbine | 18.6
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Hydraulic Plants | 209.4
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Thermal Plants | 167.1
| Tools and Equipment Result |  | 395.1
Generation Result |  |  | 3555
General Properties
Administration
|  | Purchase Office Equipment Less Than $50,000 (2024) | 50
|  | Remove Safety Hazards (2024) | 198.3
|  | General Property Rehabilitation (2024) - Hydro Place | 234
|  | Upgrade HVAC Supervisory Controllers (2024) - Hydro Place | 149.6
| Administration Result |  | 631.9
Information Systems
|  | Upgrade Energy Management System (2024) | 366.4
|  | Purchase Personal Computers (2024) | 555.9
|  | Replace Peripheral Infrastructure (2024) | 276.8
|  | Upgrade Core OT Infrastructure (2024) | 174.7
|  | Update Cyber Security Infrastructure (2024) | 281.3
| Information Systems Result |  | 1655.1
Telecontrol
|  | Replace Network Communications Equipment (2024) | 180.7
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Telecontrol | 45.6
|  | Replace 48 V Battery Banks and Chargers (2024) | 422.2
|  | Replace SONET Multiplexors (2024) | 430.4
|  | Purchase Mobile Devices (2024) | 155.6
|  | Upgrade Remote Terminal Units (2024) | 165.9
|  | Telecommunications In-Service Failure (2024) | 91.4
|  | Minor Telecommunications Enhancements (2024) | 96.9
|  | Replace CCTV Cameras (2024) | 317.6
|  | Upgrade SCADA Network (2024) | 402.3
| Telecontrol Result |  | 2308.6
General Properties Result |  |  | 4595.6
Transmission and Rural Operations
Transmission
|  | Transmission In-Service Failures (2024) | 158.5
| Transmission Result |  | 158.5
Metering
|  | Purchase Meters and Metering Equipment (2024) | 470.7
| Metering Result |  | 470.7
Tools and Equipment
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Central Region | 188.2
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Northern Region | 97
|  | Purchase Tools and Equipment Less than $50,000 (2024) - Labrador Region | 120.1
| Tools and Equipment Result |  | 405.3
Generation
|  | Diesel In-Service Failures (2024) | 488.3
| Generation Result |  | 488.3
Transmission and Rural Operations Result |  |  | 1522.8
Total Result |  |  | 9673.4

## Sched A - 2024 M.A. Over 750k
Newfoundland and Labrador Hydro
2024 Capital Budget Application
Detailed Breakdown By Minor Asset Category for 2024 expenditures (Over $750,000)
($000)
Commencement Year | 2024
Range | - multiple -
Supplemental Y/N | - multiple -
Program Subcategory | - multiple -
SY-Start Year | - multiple -
Main Cat | Sub Cat | CBA Description | 2024
Generation
Hydraulic Plant
|  | Hydraulic In-Service Failures (2024) | 1500
| Hydraulic Plant Result |  | 1500
Thermal Plant
|  | Thermal In-Service Failures (2024) | 3508.7
|  | Boiler Condition Assessment and Miscellaneous Upgrades (2024) - Holyrood | 3957.8
|  | Overhaul Unit 1 Turbine Valves and Generator (2024) - Holyrood | 5181.4
|  | Refurbish Fuel Oil Storage Tank 4 (2024) - Holyrood | 1920
| Thermal Plant Result |  | 14567.9
Generation Result |  |  | 16067.9
General Properties
Information Systems
|  | Perform Software Upgrades and Minor Enhancements (2024) | 864.2
| Information Systems Result |  | 864.2
General Properties Result |  |  | 864.2
Transmission and Rural Operations
Transmission
|  | Wood Pole Line Management (2024) | 3765.2
| Transmission Result |  | 3765.2
Distribution
|  | Distribution System In-Service Failures, Miscellaneous Upgrades, and Street Lights (2024) | 4345.4
|  | Provide Service Extensions (2024) | 4272
| Distribution Result |  | 8617.4
Tools and Equipment
|  | Replace Grader Unit V9829 (2024) - Bay d'Espoir | 836.7
|  | Replace Mobile Equipment (2024-2025) | 216.9
|  | Purchase 50' Material Handler Aerial Device on Tracked Unit (2024-2026) - Happy Valley Goose Bay | 24
| Tools and Equipment Result |  | 1077.6
Terminal Stations
|  | Terminal Station In-Service Failures (2024) | 1300
| Terminal Stations Result |  | 1300
Generation
|  | Overhaul Diesel Units (2024) | 829.2
| Generation Result |  | 829.2
Transmission and Rural Operations Result |  |  | 15589.4
Allowance for Unforeseen Items
(empty)
|  | Allowance for Unforeseen Items (2024) | 1000
| (empty) Result |  | 1000
Allowance for Unforeseen Items Result |  |  | 1000
Total Result |  |  | 33521.5

## Sched B - Under 750k
Newfoundland and Labrador Hydro
2024 Capital Budget Application
Multi-Year Projects Over $750,000
($000)
Commencement Year | - multiple -
SY-Start Year | - all -
Range | - multiple -
Supplemental Y/N | - multiple -
Program Subcategory | - multiple -
Project Type | Multi Year
Data
MY-Start Year | Investment Classification | CBA Description | 2023 & Prior Years | 2024 | 2025 | Sum of Total With Prior Year
2023
General Plant
|  | Install Fire Protection in 230 kV Stations (2023-2024) - Deer Lake | 79.2 | 535.3 |  | 614.5
|  | Water System Condition Assessment and Upgrades (2023) - Bay d'Espoir | 161 | 504.9 |  | 665.9
|  | Replace Building Exterior (2023-2024) - Postville | 124.6 | 558.7 |  | 683.3
|  | Replace HVAC System (2023-2024) - Bishop's Falls | 43.4 | 128.8 |  | 172.2
|  | Replace Mobile Equipment (2023-2024) | 541.2 | 187.3 |  | 728.5
| General Plant Result |  | 949.4 | 1915 |  | 2864.4
Renewal
|  | Install Breaker Failure Protection (2023-2024) - Sunnyside | 73.5 | 216.2 |  | 289.7
|  | Replace Oil Mist Separator (2023-2024) - Happy Valley Gas Turbine | 138.5 | 262.1 |  | 400.6
|  | Replace Data Alarm System Annunciators (2023) - Buchans | 61.2 | 104.8 |  | 166
|  | Replace Circuit Breaker Reclosing Controllers (2023-2024) - Hardwoods | 81.6 | 149.6 |  | 231.2
|  | Replace Intermediate Fuel Storage Tanks (2023-2024) - Nain | 127.4 | 593.7 |  | 721.1
| Renewal Result |  | 482.2 | 1326.4 |  | 1808.6
Service Enhancement
|  | Install Oil Spill Containment Transformer T1S (2023-2024) - Cat Arm | 155.1 | 426.5 |  | 581.6
| Service Enhancement Result |  | 155.1 | 426.5 |  | 581.6
2023 Result |  |  | 1586.7 | 3667.9 |  | 5254.6
2024
General Plant
|  | Replace Powerhouse 1 Air Conditioning Unit (2024-2025) - Bay d'Espoir |  | 57.8 | 231.2 | 289
|  | Refurbish Control Building (2024-2025) - Grandy Brook and Doyles |  | 109.4 | 444.7 | 554.1
|  | Install Fire Protection in 230 kV Stations (2024–2025) - Voisey's Bay |  | 53.8 | 599 | 652.8
| General Plant Result |  |  | 221 | 1274.9 | 1495.9
Mandatory
|  | Upgrade Station Lighting (2024-2025) - Bottom Waters, Deer Lake, Doyles, Indian River, and Western Avalon Terminal Stations |  | 91.6 | 429 | 520.6
| Mandatory Result |  |  | 91.6 | 429 | 520.6
Renewal
|  | Replace Annunciator - Phase 2 (2024-2025) - Bay d'Espoir |  | 294.1 | 187.5 | 481.6
|  | Replace Terminal Station Battery Banks and Chargers (2024–2025) |  | 71.8 | 120.9 | 192.7
|  | Replace Annunciator Panels (2024-2025) - Cat Arm |  | 160.2 | 191.2 | 351.4
|  | Upgrade UPS 1 & 2 (2024-2025) - Holyrood |  | 263 | 107.6 | 370.6
|  | Upgrade Unit 1 Control System (2024-2025) - Holyrood |  | 468.3 | 184.3 | 652.6
|  | Upgrade DCS Hardware - Units 1 and 2 (2024-2025) - Holyrood |  | 195.2 | 277.3 | 472.5
|  | Upgrade Data Alarm Systems (2024–2025) - Western Avalon Terminal Station |  | 137 | 156.9 | 293.9
|  | Replace Circuit Breaker Reclosing Controllers (2024–2025) - TL247 |  | 112.4 | 215.8 | 328.2
|  | Upgrade Distribution (2024-2025) - Bay d'Espoir Terminal Station 2 |  | 93.2 | 331.5 | 424.7
| Renewal Result |  |  | 1795.2 | 1773 | 3568.2
Service Enhancement
|  | Construct Maintenance Platform (2024-2025) - Holyrood Gas Turbine |  | 130.5 | 228.7 | 359.2
|  | Upgrade Instrumentation (2024-2025) - Hardwoods Gas Turbine |  | 60.9 | 157.2 | 218.1
| Service Enhancement Result |  |  | 191.4 | 385.9 | 577.3
2024 Result |  |  |  | 2299.2 | 3862.8 | 6162
Total Result |  |  | 1586.7 | 5967.1 | 3862.8 | 11416.6

## Sched B - Over 750k
Newfoundland and Labrador Hydro
2024 Capital Budget Application
Multi-Year Projects Over $750,000
($000)
Commencement Year | - multiple -
SY-Start Year | - all -
Range | - multiple -
Supplemental Y/N | - multiple -
Program Subcategory | - multiple -
Project Type | Multi Year
Data
MY-Start Year | Investment Classification | CBA Description | 2023 & Prior Years | 2024 | 2025 | Sum of Total With Prior Year
2021
Renewal
|  | Refurbish Ebbegunbaeg Control Structure | 9945.2 | 2781.6 | 4952.2 | 17679
| Renewal Result |  | 9945.2 | 2781.6 | 4952.2 | 17679
System Growth
|  | Wabush Terminal Station Upgrades | 8870.1 | 3808 |  | 12678.1
|  | Additions for Load - Wabush Substation Upgrades | 7439.7 | 2739.9 | 514.5 | 10694.1
| System Growth Result |  | 16309.8 | 6547.9 | 514.5 | 23372.2
2021 Result |  |  | 26255 | 9329.5 | 5466.7 | 41051.2
2022
General Plant
|  | Purchase 85' Material Handler Aerial Device on Track Unit | 1286.1 | 67.8 |  | 1353.9
|  | Purchase 46' Material Handler Aerial Device on Track Unit | 719.2 | 38.8 |  | 758
|  | Replace Light- and Heavy-Duty Vehicles (2022-2024) | 1162.2 | 2319.6 |  | 3481.8
| General Plant Result |  | 3167.5 | 2426.2 |  | 5593.7
Renewal
|  | Diesel Genset Replacement Unit 2012 - L'Anse-Au-Loup | 2853.1 | 210.2 |  | 3063.3
| Renewal Result |  | 2853.1 | 210.2 |  | 3063.3
Service Enhancement
|  | Replace Metering System | 4881.2 | 994.6 |  | 5875.8
| Service Enhancement Result |  | 4881.2 | 994.6 |  | 5875.8
2022 Result |  |  | 10901.8 | 3631 |  | 14532.8
2023
General Plant
|  | Replace Light- and Heavy-Duty Vehicles (2023-2025) | 1308.1 | 2584.6 | 473.3 | 4366
|  | Upgrade Water and Fire Suppression Systems (2023-2024) - Bishop's Falls | 353.7 | 2886.3 |  | 3240
|  | Replace Diesel Shop Building (2023-2025) - Bishop's Falls | 168 | 1254.1 | 889.9 | 2312
| General Plant Result |  | 1829.8 | 6725 | 1363.2 | 9918
Mandatory
|  | Replace Terminal Station Lighting (2023-2024) | 323.3 | 594.1 |  | 917.4
| Mandatory Result |  | 323.3 | 594.1 |  | 917.4
Renewal
|  | Terminal Station Renewal Program (2023-2024) | 1733.7 | 5584.5 |  | 7318.2
|  | Circuit Breakers Renewal Program (2023-2024) | 216.9 | 3595.1 |  | 3812
|  | Diesel Genset Replacement Program (2023-2025) | 819.1 | 174 | 1883.1 | 3126.2
|  | Replace Diesel Genset 1 (2023-2024) - Ebbegunbaeg | 298 | 728.3 |  | 1026.3
|  | Refurbish Superstructure (2023-2024) - Salmon River Spillway | 328.3 | 2500 |  | 2828.3
|  | Replace Powerhouse Station Service Panel (2023-2024) - Upper Salmon | 591.8 | 976.7 |  | 1568.5
|  | Major Condition Assessment and Miscellaneous Refurbishments Synchronous Condenser 1 and 2 (2023-2024) - Wabush Terminal Station | 577.2 | 516.1 |  | 1093.3
|  | Replace Power Line Carrier (2023–2024) - TL223 and TL224 | 105.3 | 852.4 |  | 957.7
| Renewal Result |  | 4670.3 | 14927.1 | 1883.1 | 21730.5
Service Enhancement
|  | Upgrade of Worst-Performing Distribution Feeders (2023-2024) | 73.4 | 1372.6 |  | 1446
| Service Enhancement Result |  | 73.4 | 1372.6 |  | 1446
System Growth
|  | Additions for Load Growth - Upgrade Transformer Capacity (2023-2024) - Jean Lake Terminal Station | 580 | 0 | 5436.1 | 6016.1
| System Growth Result |  | 580 | 0 | 5436.1 | 6016.1
2023 Result |  |  | 7476.8 | 23618.8 | 8682.4 | 40028
2024
General Plant
|  | Replace MDR8000 Microwave Radios (2024-2025) |  | 953.5 | 500.3 | 1453.8
|  | Replace Powerhouse 1 Roof (2024-2025) - Bay d'Espoir |  | 140.2 | 1819.2 | 1959.4
|  | Refurbish Outbuilding and Powerhouse Building Envelopes (2024-2025) - Holyrood |  | 156.2 | 1039.4 | 1195.6
|  | Purchase Accommodations Trailer (2024-2025) - Makkovik and Cartwright |  | 130.9 | 1420.2 | 1551.1
|  | Replace Light- and Heavy-Duty Vehicles (2024-2026) |  | 1479.1 | 4148.8 | 5636.3
|  | Replace VHF Radio System (2024-2025) |  | 1261.6 | 290.6 | 1552.2
| General Plant Result |  |  | 4121.5 | 9218.5 | 13348.4
Renewal
|  | Replace Power Line Carrier (2024-2025) - TL247 |  | 87.2 | 667.4 | 754.6
|  | Replace Instrument Transformers (2024–2025) |  | 154.9 | 714.8 | 869.7
|  | Replace Protective Relays (2024–2025) |  | 1388.4 | 2050.7 | 3439.1
|  | Replace Disconnects (2024–2025) |  | 127.4 | 1358.1 | 1485.5
|  | Upgrade Power Transformers (2024-2025) |  | 864.6 | 2711.3 | 3575.9
|  | Flatten Downstream Slope (2024-2025) - Hinds Lake |  | 276.1 | 2953.4 | 3229.5
|  | Refurbish Surge Tank 1 (2024-2025) - Bay d'Espoir |  | 175.8 | 2111.4 | 2287.2
|  | Renew Circuit Breakers (2024–2025) |  | 183.9 | 2779.3 | 2963.2
|  | Renew Distribution Feeders (2024-2025) |  | 1287.3 | 1245.1 | 2532.4
|  | Refurbish Intake 1 (2024-2025) - Bay d'Espoir |  | 272.1 | 3071.9 | 3344
|  | Replace Diesel Gensets (2024-2026) |  | 535.8 | 478 | 4916.1
| Renewal Result |  |  | 5353.5 | 20141.4 | 29397.2
Service Enhancement
|  | Automate Bulk Metering (2024-2026) |  | 302.6 | 214.4 | 752.3
|  | Upgrade Worst-Performing Distribution Feeders (2024-2025) |  | 1064.3 | 2227.4 | 3291.7
|  | [] | 0 | 0 | 0 | 0
| Service Enhancement Result |  | 0 | 1366.9 | 2441.8 | 4044
2024 Result |  |  | 0 | 10841.9 | 31801.7 | 46789.6
Total Result |  |  | 44633.6 | 47421.2 | 45950.8 | 142401.6